## View 01
. | Update Status | Percent complete | Line identifier | Finished | Description | Duration | Start no earlier than | Planned start | Planned finish | Resources assigned | Remaining Load (Hours) | Predecessor | Successor | Go On Time slippage (end date) | Is a WBS element?
| Confirmed | 87.2363 | 43 | NO | SCC Sub System Deployment & Warranty | 1569d |  | 2021-06-09 08:00 | 2027-12-06 16:00 |  | 10853.8581 |  |  | -362d | YES
| Confirmed | 92.1918 | 44 | NO | SCC Sub Systems Engineering & Design | 1339d |  | 2021-06-09 08:00 | 2026-12-21 16:00 |  | 6340.3985 |  |  | -80d | YES
| Confirmed | 62.3834 | 819 | NO | SCC Sub Systems V&C | 1569d |  | 2021-06-09 08:00 | 2027-12-06 16:00 |  | 4464.4596 |  |  | -362d | YES
| Confirmed | 81.6401 | 820 | NO | V&V General | 1553d |  | 2021-07-01 08:00 | 2027-12-06 16:00 |  | 129.8596 |  |  | -486d | YES
| Confirmed | 58.4717 | 835 | NO | V&V SCADA | 1474d |  | 2021-06-09 08:00 | 2027-07-15 16:00 |  | 4334.6 |  |  | -218d | YES
| Confirmed | 53.6445 | 932 | NO | Montagem Plataforma - SCADA | 1399d |  | 2021-06-09 08:00 | 2027-03-25 16:00 |  | 630 |  |  | -132d | YES
| Future Activity | 0 | 972 | NO | Configuração Plataforma - TEN/TES/TSG - CWE - FAT (T3/T4) v1 | 57d | 2024-11-21 08:00 | 2026-09-30 08:00 | 2026-12-22 16:00 |  | 90 |  |  | -39d | YES
| Future Activity | 0 | 976 | NO | Configuração Plataforma SCADA CWE FAT 1 (T3/T4) | 5d |  | 2026-11-12 08:00 | 2026-11-18 16:00 | Pereira Nicolas | 18 | 973SS | 3FS | -8d | NO
| Future Activity | 0 | 973 | NO | Configuração Ferramenta SCADA - TEN CWE - FAT 1 (T3/T4) | 3d |  | 2026-11-12 08:00 | 2026-11-16 16:00 | Silva Alexandre | 18 | 3087FS | 976SS;996FS | -10d | NO
| Future Activity | 0 | 974 | NO | Configuração Ferramenta SCADA - TES CWE - FAT 1 (T3/T4) | 3d |  | 2026-09-30 08:00 | 2026-10-02 16:00 | Silva Alexandre | 27 | 3089FS | 997FS | 13d | NO
| Future Activity | 0 | 975 | NO | Configuração Ferramenta SCADA - TSG CWE - FAT 1 (T3/T4) | 3d |  | 2026-12-18 08:00 | 2026-12-22 16:00 | Silva Alexandre | 27 | 997FS;3091FS | 998FS | -39d | NO
| Future Activity | 0 | 977 | NO | Configuração Plataforma - TEN/TES/TSG - CWE - FAT 2 (T1/T2/T5) | 32d | 2024-11-21 08:00 | 2027-01-11 08:00 | 2027-03-01 16:00 |  | 90 |  |  | -20424d | YES
| Future Activity | 0 | 981 | NO | Configuração Plataforma SCADA CWE FAT 2 (T1/T2/T5) | 5d |  | 2027-01-18 08:00 | 2027-01-22 16:00 | Pereira Nicolas | 18 | 978SS |  |  | NO
| Future Activity | 0 | 978 | NO | Configuração Ferramenta SCADA - TEN CWE - FAT 2 (T1/T2/T5) | 3d |  | 2027-01-18 08:00 | 2027-01-20 16:00 | Silva Alexandre | 18 | 3094FS;3101FS | 981SS;1001FS |  | NO
| Future Activity | 0 | 979 | NO | Configuração Ferramenta SCADA - TES CWE - FAT 2 (T1/T2/T5) | 3d |  | 2027-01-11 08:00 | 2027-01-13 16:00 | Silva Alexandre | 27 | 3096FS;3103FS | 1002FS |  | NO
| Future Activity | 0 | 980 | NO | Configuração Ferramenta SCADA - TSG CWE - FAT 2 (T1/T2/T5) | 3d |  | 2027-02-25 08:00 | 2027-03-01 16:00 | Silva Alexandre | 27 | 1002FS;3098FS;3105FS | 1003FS |  | NO
| Future Activity | 0 | 982 | NO | Configuração Plataforma - TEN/TES/TSG - CWE - FAT (T6/T7) v1 | 50d | 2024-11-21 08:00 | 2027-01-11 08:00 | 2027-03-25 16:00 |  | 90 |  |  | -20448d | YES
| Future Activity | 0 | 986 | NO | Configuração Plataforma SCADA CWE FAT (T6/T7) | 5d |  | 2027-01-11 08:00 | 2027-01-15 16:00 | Pereira Nicolas | 18 | 983SS |  |  | NO
| Future Activity | 0 | 983 | NO | Configuração Ferramenta SCADA - TEN CWE - FAT (T6/T7) | 3d |  | 2027-01-11 08:00 | 2027-01-13 16:00 | Silva Alexandre | 18 | 3103FS | 986SS;1006FS |  | NO
| Future Activity | 0 | 984 | NO | Configuração Ferramenta SCADA - TES CWE - FAT (T6/T7) | 3d |  | 2027-03-23 08:00 | 2027-03-25 16:00 | Silva Alexandre | 27 | 3110FS | 1007FS |  | NO
| Future Activity | 0 | 985 | NO | Configuração Ferramenta SCADA - TSG CWE - FAT (T6/T7) | 3d |  | 2027-02-25 08:00 | 2027-03-01 16:00 | Silva Alexandre | 27 | 3105FS | 1008FS |  | NO
| Confirmed | 99.9887 | 933 | NO | Configuração Plataforma - TEN/TES/TSG - CWI - FAT | 1176d |  | 2021-06-09 08:00 | 2026-04-23 16:00 |  | 198 |  |  | -51d | YES
| Future Activity | 0 | 941 | NO | Arrumar/Melhorias scripts TEN/TSG | 5d | 2026-04-01 08:00 | 2026-04-01 08:00 | 2026-04-08 16:00 | Paoli Camila | 27 |  |  |  | NO
| Future Activity | 0 | 955 | NO | Atualização PTS pós FAT - TEN/TES/TSG | 5d | 2026-04-01 08:00 | 2026-04-15 08:00 | 2026-04-23 16:00 | Silva Alexandre | 45 | 951FS;1039FS;1045FS |  |  | NO
| Future Activity | 0 | 951 | NO | Atualização/Melhorias Ferramenta SCADA pós FAT - TEN/TES/TSG CWI - FAT 1 | 7d | 2026-04-06 08:00 | 2026-04-06 08:00 | 2026-04-14 16:00 | Silva Alexandre | 63 |  | 955FS |  | NO
| Future Activity | 0 | 953 | NO | Configuração Plataforma SCADA TEN - DEMO CFE | 3d |  | 2026-03-03 08:00 | 2026-03-05 16:00 | Silva Alexandre | 27 | 954FS;3073FS | 1041FS |  | NO
| Future Activity | 0 | 956 | NO | Configuração de Plataforma Pós Correções CRs - TSG/TES CWI - T1 a T5 FAT | 1d | 2026-04-07 08:00 | 2026-04-09 08:00 | 2026-04-09 16:00 | Silva Alexandre | 9 | 2925FS;2927FS;3239FS;3256FS | 1035FS;1047FS |  | NO
| Future Activity | 0 | 957 | NO | Configuração Plataforma SCADA TEN/TES/TSG - DEMO Pós correções | 3d |  | 2026-03-02 08:00 | 2026-03-04 16:00 | Silva Alexandre | 27 | 3075SS | 1046FS;1048FS |  | NO
| Future Activity | 0 | 959 | NO | Configuração Plataforma - Territory M/ Geo T / Alarm | 35d |  | 2026-09-22 08:00 | 2026-11-11 16:00 |  | 162 |  |  | -308d | YES
| Future Activity | 0 | 961 | NO | Desenvovimento API S2K-Phoenix (DEMO) | 10d | 2025-11-03 08:00 | 2026-09-22 08:00 | 2026-10-05 16:00 | Silva Alexandre | 90 | 3211FS | 2857FS | -320d | NO
| Future Activity | 0 | 960 | NO | Configuração Ferramenta SCADA - Territory M/ Geo T / Alarm - Demo 3 Interno - FAT | 5d |  | 2026-09-22 08:00 | 2026-09-28 16:00 | Silva Alexandre | 45 | 3121FS | 989FS | -320d | NO
| Future Activity | 0 | 962 | NO | Configuração Ferramenta SCADA - Territory M/ Geo T / Alarm - Demo 3 Cliente - FAT 2 | 3d |  | 2026-11-09 08:00 | 2026-11-11 16:00 | Silva Alexandre | 27 | 3354FS | 991FS | -308d | NO
| Confirmed | 25.5711 | 987 | NO | Testes em Plataforma - SCADA | 1474d |  | 2021-06-09 08:00 | 2027-07-15 16:00 |  | 3506.6 |  |  | -218d | YES
| Confirmed | 46.371 | 993 | NO | FAT 1 CWE TEN/TES/TSG - Tramos 1, 2, 3 & 4 (v1) | 1414d |  | 2021-06-09 08:00 | 2027-04-16 16:00 |  | 2120.6 |  |  | -128d | YES
| Future Activity | 0 | 1005 | NO | FAT SCADA CWE TEN/TES/TSG - (T6/T7) v1 | 62d |  | 2027-01-14 08:00 | 2027-04-16 16:00 |  | 405 |  |  | -574d | YES
| Future Activity | 0 | 1007 | NO | FAT SCADA - TES CWE (T6/T7) v1 | 15d | 2026-01-05 08:00 | 2027-03-29 08:00 | 2027-04-16 16:00 | Pereira Nicolas | 135 | 984FS | 1009FS | -603d | NO
| Future Activity | 0 | 1008 | NO | FAT SCADA - TSG CWE (T6/T7) v1 | 15d | 2026-01-05 08:00 | 2027-03-02 08:00 | 2027-03-22 16:00 | Pereira Nicolas | 135 | 985FS | 1009FS | -578d | NO
| Future Activity | 0 | 1006 | NO | FAT SCADA - TEN CWE (T6/T7) v1 | 15d | 2026-01-05 08:00 | 2027-01-14 08:00 | 2027-02-04 16:00 | Pereira Nicolas | 135 | 983FS | 1009FS | -503d | NO
| Future Activity | 0 | 1009 | NO | Fim Testes Plataf - SCADA TES, TEN and TSG - V1 - Tramo 6 & 7 v1 | 0d |  | 2027-04-17 08:00 | 2027-04-16 16:00 |  | 0 | 1006FS;1007FS;1008FS | 1063FS;1064FS | -574d | NO
| Confirmed | 99.981 | 1010 | NO | Baseline CWI | 1275d |  | 2021-06-09 08:00 | 2026-09-17 16:00 |  | 932.6 |  |  | -660d | YES
| Confirmed | 17.3913 | 1027 | NO | FAT TEN/TES/TSG CWI | 1275d |  | 2021-06-09 08:00 | 2026-09-17 16:00 |  | 932.6 |  |  | -20259d | YES
| Future Activity | 0 | 1041 | NO | FAT Interno - TEN CWI - DEMO CFE | 3d |  | 2026-03-06 08:00 | 2026-03-10 16:00 | Paoli Camila,Rodrigues Enzo | 37 | 953FS;3074FS | 1028FS;1046FF;2924SS+13d;2931FS;3313FS-3d;3337SS+13d |  | NO
| Future Activity | 0 | 1028 | NO | RTE - TEN - CWI DEMO CFE | 2d |  | 2026-03-11 08:00 | 2026-03-12 16:00 | Paoli Camila,Pereira Nicolas | 27 | 1041FS | 1032FS |  | NO
| Future Activity | 0 | 1046 | NO | FAT Interno - TES CWI - DEMO Pós Correções | 4d |  | 2026-03-05 08:00 | 2026-03-10 16:00 | Silva Alexandre | 36 | 957FS;1041FF;2929FS;3238FS | 1040FS;1048FF;1049FS |  | NO
| Future Activity | 0 | 1048 | NO | FAT Interno - TSG CWI - DEMO Pós Correções | 3d |  | 2026-03-06 08:00 | 2026-03-10 16:00 | Pereira Nicolas | 27 | 957FS;1046FF;3311FS | 1049FS;1050FS |  | NO
| Future Activity | 0 | 1049 | NO | RTE - Relatório de Conclusão de Teste - TEN/TES/TSG - CWI - DEMO Pós Correções | 2d |  | 2026-03-11 08:00 | 2026-03-12 16:00 | Pereira Nicolas | 18 | 1046FS;1048FS | 2907FS |  | NO
| Future Activity | 0 | 1040 | NO | FAT Interno - TES CWI - T1 a T5 | 17d |  | 2026-03-11 08:00 | 2026-04-02 16:00 | Paoli Camila,Pereira Nicolas,Silva Alexandre | 180 | 949FS;1046FS;3079FS+4d | 1030FS;2925SS+5d;3239SS+5d |  | NO
| Future Activity | 0 | 1050 | NO | FAT Interno - TSG CWI - T1 a T5 | 17d |  | 2026-03-11 08:00 | 2026-04-02 16:00 | Paoli Camila,Pereira Nicolas | 98 | 949FS;1048FS;3081FS+4d | 1031FS;2927SS+5d;3256SS+5d |  | NO
| Future Activity | 0 | 1031 | NO | RTE - Relatório de Conclusão de Teste - TSG- CWI FAT | 2d |  | 2026-04-06 08:00 | 2026-04-07 16:00 | Pereira Nicolas | 9 | 1050FS | 1032FS |  | NO
| Future Activity | 0 | 1030 | NO | RTE - Relatório de Conclusão de Teste - TES - CWI FAT | 2d |  | 2026-04-06 08:00 | 2026-04-07 16:00 | Silva Alexandre | 9 | 1040FS | 1032FS |  | NO
| Future Activity | 0 | 1032 | NO | RVT - TES/TSG - CWI FAT | 3d |  | 2026-04-08 08:00 | 2026-04-10 16:00 | Pereira Nicolas | 27 | 1028FS;1030FS;1031FS | 1033FS |  | NO
| Future Activity | 0 | 1033 | NO | V&V Report - TES/TSG - CWI FAT | 3d |  | 2026-04-13 08:00 | 2026-04-15 16:00 | Pereira Nicolas | 27 | 1032FS | 3FS |  | NO
| Future Activity | 0 | 1047 | NO | Reteste Correções CRs - TES CWI - T1 a T5 FAT | 8d |  | 2026-04-10 08:00 | 2026-04-23 16:00 | Senna Samya | 72 | 956FS | 1043FS |  | NO
| Future Activity | 0 | 1035 | NO | Reteste Correções CRs - TSG CWI - T1 a T5 FAT | 8d |  | 2026-04-10 08:00 | 2026-04-23 16:00 | Silva Alexandre | 72 | 956FS | 1042FS |  | NO
| Future Activity | 0 | 1042 | NO | RTE - Relatório de Conclusão de Teste - TSG- CWI FAT | 2d |  | 2026-04-24 08:00 | 2026-04-27 16:00 | Senna Samya | 9 | 1035FS | 1038FS |  | NO
| Future Activity | 0 | 1043 | NO | RTE - Relatório de Conclusão de Teste - TES- CWI FAT | 2d |  | 2026-04-24 08:00 | 2026-04-27 16:00 | Paoli Camila,Senna Samya | 25 | 1047FS | 1038FS |  | NO
| Future Activity | 0 | 1038 | NO | FAT - RVT - TES/TSG - CWI | 8d |  | 2026-04-28 08:00 | 2026-05-08 16:00 | Paoli Camila,Pereira Nicolas | 97.6 | 1042FS;1043FS | 1037FS;3006FS |  | NO
| Future Activity | 0 | 1034 | NO | Reteste Correções CRs - TEN CWI - T1 a T7 | 8d |  | 2026-08-24 08:00 | 2026-09-02 16:00 | Silva Alexandre | 72 | 2924FS;3337FS | 1036FS |  | NO
| Future Activity | 0 | 1036 | NO | RTE - Relatório de Conclusão de Teste - TEN - CWI - T1 a T7 | 2d |  | 2026-09-03 08:00 | 2026-09-04 16:00 | Senna Samya | 18 | 1034FS | 3FS;1037FS |  | NO
| Future Activity | 0 | 1037 | NO | V&V Report - TES/TSG - CWI T1 a T7 | 8d |  | 2026-09-08 08:00 | 2026-09-17 16:00 | Pereira Nicolas | 72 | 1036FS;1038FS | 3FS |  | NO
| Future Activity | 0 | 994 | NO | Baseline CWE | 106d |  | 2026-10-05 08:00 | 2027-03-16 16:00 |  | 783 |  |  | -97d | YES
| Future Activity | 0 | 995 | NO | FAT SCADA CWE TEN/TES/TSG (T3/T4) v1 | 65d |  | 2026-10-05 08:00 | 2027-01-12 16:00 |  | 400 |  |  | -20376d | YES
| Future Activity | 0 | 996 | NO | FAT SCADA - TEN CWE (T3/T4) v1 | 6d |  | 2026-11-17 08:00 | 2026-11-25 16:00 | Pereira Nicolas,Silva Alexandre | 108 | 973FS | 3FS |  | NO
| Future Activity | 0 | 997 | NO | FAT SCADA - TES CWE (T3/T4) v1 | 9d |  | 2026-10-05 08:00 | 2026-10-16 16:00 | Pereira Nicolas,Silva Alexandre | 162 | 974FS | 975FS |  | NO
| Future Activity | 0 | 998 | NO | FAT SCADA - TSG CWE (T3/T4) v1 | 6d |  | 2026-12-23 08:00 | 2027-01-05 16:00 | Pereira Nicolas,Silva Alexandre | 108 | 975FS | 999FS |  | NO
| Future Activity | 0 | 999 | NO | RTE - Relatório de Conclusão de Teste - FAT SCADA - CWE (T3/T4) v1 | 5d |  | 2027-01-06 08:00 | 2027-01-12 16:00 | Silva Alexandre | 22 | 998FS | 3FS |  | NO
| Future Activity | 0 | 1000 | NO | FAT SCADA CWE TEN/TES/TSG (T1/T2) v1 | 40d |  | 2027-01-14 08:00 | 2027-03-16 16:00 |  | 383 |  |  | -97d | YES
| Future Activity | 0 | 1001 | NO | FAT SCADA - TEN CWE (T1/T2) v1 | 6d |  | 2027-01-21 08:00 | 2027-01-29 16:00 | Pereira Nicolas,Silva Alexandre | 108 | 978FS | 3FS | -65d | NO
| Future Activity | 0 | 1002 | NO | FAT SCADA - TES CWE (T1/T2) v1 | 8d |  | 2027-01-14 08:00 | 2027-01-26 16:00 | Pereira Nicolas,Silva Alexandre | 144 | 979FS | 980FS | -77d | NO
| Future Activity | 0 | 1003 | NO | FAT SCADA - TSG CWE (T1/T2) v1 | 6d |  | 2027-03-02 08:00 | 2027-03-09 16:00 | Pereira Nicolas,Silva Alexandre | 108 | 980FS | 1004FS | -97d | NO
| Future Activity | 0 | 1004 | NO | RTE - Relatório de Conclusão de Teste - FAT SCADA - CWE (T1/T2) v1 | 5d |  | 2027-03-10 08:00 | 2027-03-16 16:00 | Silva Alexandre | 23 | 1003FS | 3FS | -97d | NO
| Confirmed | 16.2599 | 1051 | NO | Tramos 5, 6 & 7 | 672d |  | 2024-09-30 08:00 | 2027-07-15 16:00 |  | 1296 |  |  | -472d | YES
| Future Activity | 0 | 1062 | NO | Baseline V2 - SCADA - Tramo 6 | 30d |  | 2027-04-19 08:00 | 2027-06-02 16:00 |  | 270 |  |  | -476d | YES
| Future Activity | 0 | 1064 | NO | Testes em Plataforma - SCADA TEN (T06 / V02) | 10d |  | 2027-04-19 08:00 | 2027-05-03 16:00 | GENERICO - V&V | 90 | 1009FS;2008FS+1d;CT4441_Tren Maya_S_PMG_SAO:99FS | 1063FS;1066FS | -474d | NO
| Future Activity | 0 | 1065 | NO | Testes em Plataforma - SCADA TSG (T06 / V02) | 10d |  | 2027-05-18 08:00 | 2027-06-02 16:00 | GENERICO - V&V | 90 | 1063FS;2014FS+1d;CT4441_Tren Maya_S_PMG_SAO:100FS | 1066FS | -476d | NO
| Future Activity | 0 | 1063 | NO | Testes em Plataforma - SCADA TES (T06 / V02) | 10d |  | 2027-05-04 08:00 | 2027-05-17 16:00 | Pereira Nicolas | 90 | 1009FS;1064FS;2000FS+1d;CT4441_Tren Maya_S_PMG_SAO:98FS | 1065FS;1066FS | -474d | NO
| Future Activity | 0 | 1066 | NO | Fim Testes Plataf - SCADA TES, TEN and TSG (T06 / V02) | 0d |  | 2027-06-03 08:00 | 2027-06-02 16:00 |  | 0 | 1063FS;1064FS;1065FS | 1079FS | -476d | NO
| Future Activity | 0 | 1077 | NO | Baseline V3 - SCADA - Tramo 6 | 30d |  | 2027-06-03 08:00 | 2027-07-15 16:00 |  | 270 |  |  | -472d | YES
| Future Activity | 0 | 1079 | NO | Testes em Plataforma - SCADA TEN (T06 / V03) | 10d |  | 2027-06-03 08:00 | 2027-06-16 16:00 | GENERICO - V&V | 90 | 1066FS;2071FS+1d | 1080FS;1081FS | -471d | NO
| Future Activity | 0 | 1080 | NO | Testes em Plataforma - SCADA TSG (T06 / V03) | 10d |  | 2027-06-17 08:00 | 2027-06-30 16:00 | GENERICO - V&V | 90 | 1079FS;2077FS+1d | 1078FS;1081FS | -471d | NO
| Future Activity | 0 | 1078 | NO | Testes em Plataforma - SCADA TES (T06 / V03) | 10d |  | 2027-07-01 08:00 | 2027-07-15 16:00 | Pereira Nicolas | 90 | 1080FS;2063FS+1d | 1081FS | -472d | NO
| Future Activity | 0 | 1081 | NO | Fim Testes Plataf - SCADA TES, TEN and TSG (T06 / V03) | 0d |  | 2027-07-16 08:00 | 2027-07-15 16:00 |  | 0 | 1078FS;1079FS;1080FS | 3FS | -472d | NO
| Future Activity | 0 | 1067 | NO | Baseline V2 - SCADA - Tramo 7 | 24d |  | 2026-12-08 08:00 | 2027-01-14 16:00 |  | 189 |  |  | -345d | YES
| Future Activity | 0 | 1069 | NO | Testes em Plataforma - SCADA TEN (T07 / V02) | 7d | 2026-01-05 08:00 | 2026-12-08 08:00 | 2026-12-16 16:00 | GENERICO - V&V | 63 | 2029FS+1d;CT4441_Tren Maya_S_PMG_SAO:99FS | 1070FS;1071FS | -341d | NO
| Future Activity | 0 | 1070 | NO | Testes em Plataforma - SCADA TSG (T07 / V02) | 7d |  | 2026-12-22 08:00 | 2027-01-05 16:00 | GENERICO - V&V | 63 | 1069FS;2035FS+1d;CT4441_Tren Maya_S_PMG_SAO:100FS | 1068FS;1071FS | -347d | NO
| Future Activity | 0 | 1068 | NO | Testes em Plataforma - SCADA TES (T07 / V02) | 7d |  | 2027-01-06 08:00 | 2027-01-14 16:00 | Pereira Nicolas | 63 | 1070FS;2021FS+1d;CT4441_Tren Maya_S_PMG_SAO:98FS | 1071FS | -345d | NO
| Future Activity | 0 | 1071 | NO | Fim Testes Plataf - SCADA TES, TEN and TSG (T07 / V02) | 0d |  | 2027-01-15 08:00 | 2027-01-14 16:00 |  | 0 | 1068FS;1069FS;1070FS | 1084FS | -345d | NO
| Future Activity | 0 | 1082 | NO | Baseline V3 - SCADA - Tramo 7 | 21d |  | 2027-01-15 08:00 | 2027-02-18 16:00 |  | 189 |  |  | -346d | YES
| Future Activity | 0 | 1084 | NO | Testes em Plataforma - SCADA TEN (T07 / V03) | 7d |  | 2027-01-15 08:00 | 2027-01-26 16:00 | Pereira Nicolas | 63 | 1071FS;2092FS+1d | 1085FS;1086FS | -348d | NO
| Future Activity | 0 | 1085 | NO | Testes em Plataforma - SCADA TSG (T07 / V03) | 7d |  | 2027-01-27 08:00 | 2027-02-04 16:00 | GENERICO - V&V | 63 | 1084FS;2098FS+1d | 1083FS;1086FS | -343d | NO
| Future Activity | 0 | 1083 | NO | Testes em Plataforma - SCADA TES (T07 / V03) | 7d |  | 2027-02-05 08:00 | 2027-02-18 16:00 | GENERICO - V&V | 63 | 1085FS;2084FS+1d | 1086FS | -346d | NO
| Future Activity | 0 | 1086 | NO | Fim Testes Plataf - SCADA TES, TEN and TSG (T07 / V03) | 0d |  | 2027-02-19 08:00 | 2027-02-18 16:00 |  | 0 | 1083FS;1084FS;1085FS | 3FS | -346d | NO
| Confirmed | 66.6667 | 1052 | NO | Baseline V1 - SCADA - Tramo 5 | 490d |  | 2024-09-30 08:00 | 2026-10-13 16:00 |  | 0 |  |  | -319d | YES
| Future Activity | 0 | 1054 | NO | Testes em Plataforma - SCADA TEN - V1 - Tramo 5 | 15d | 2025-10-01 08:00 | 2026-09-22 08:00 | 2026-10-13 16:00 | GENERICO - V&V | 0 | 3121FS;CT4441_Tren Maya_S_PMG_SAO:86FS | 1056FS | -319d | NO
| Future Activity | 0 | 1056 | NO | Fim Testes Plataf - SCADA TES, TEN and TSG - V1 - Tramo 5 | 0d |  | 2026-10-14 08:00 | 2026-10-13 16:00 |  | 0 | 1053FS;1054FS;1055FS | 1059FS | -319d | NO
| Future Activity | 0 | 1057 | NO | Baseline V2 - SCADA - Tramo 5 | 21d |  | 2026-10-14 08:00 | 2026-11-12 16:00 |  | 189 |  |  | -308d | YES
| Future Activity | 0 | 1059 | NO | Testes em Plataforma - SCADA TEN (T05 / V02) | 7d | 2025-01-13 08:00 | 2026-10-14 08:00 | 2026-10-22 16:00 | GENERICO - V&V | 63 | 1056FS;1987FS+1d | 1060FS;1061FS | -317d | NO
| Future Activity | 0 | 1060 | NO | Testes em Plataforma - SCADA TSG (T05 / V02) | 7d |  | 2026-10-23 08:00 | 2026-11-03 16:00 | GENERICO - V&V | 63 | 1059FS;1993FS+1d | 1058FS;1061FS | -320d | NO
| Future Activity | 0 | 1058 | NO | Testes em Plataforma - SCADA TES (T05 / V02) | 7d |  | 2026-11-04 08:00 | 2026-11-12 16:00 | GENERICO - V&V | 63 | 1060FS;1979FS+1d | 1061FS | -308d | NO
| Future Activity | 0 | 1061 | NO | Fim Testes Plataf - SCADA TES, TEN and TSG (T05 / V02) | 0d |  | 2026-11-13 08:00 | 2026-11-12 16:00 |  | 0 | 1058FS;1059FS;1060FS | 1074FS;CT4441_S_SDI_MAD_Schedule (TREN MAYA):598FS | -308d | NO
| Future Activity | 0 | 1072 | NO | Baseline V3 - SCADA - Tramo 5 | 21d |  | 2026-11-13 08:00 | 2026-12-14 16:00 |  | 189 |  |  | -311d | YES
| Future Activity | 0 | 1074 | NO | Testes em Plataforma - SCADA TEN (T05 / V03) | 7d |  | 2026-11-13 08:00 | 2026-11-24 16:00 | GENERICO - V&V | 63 | 1061FS;2050FS+1d | 1075FS;1076FS;1112FS | -309d | NO
| Future Activity | 0 | 1075 | NO | Testes em Plataforma - SCADA TSG (T05 / V03) | 7d |  | 2026-11-25 08:00 | 2026-12-03 16:00 | GENERICO - V&V | 63 | 1074FS;2056FS+1d | 1073FS;1076FS;1112FS | -309d | NO
| Future Activity | 0 | 1073 | NO | Testes em Plataforma - SCADA TES (T05 / V03) | 7d |  | 2026-12-04 08:00 | 2026-12-14 16:00 | GENERICO - V&V | 63 | 1075FS;2042FS+1d | 1076FS;1112FS | -311d | NO
| Future Activity | 0 | 1076 | NO | Fim Testes Plataf - SCADA TES, TEN and TSG (T05 / V03) | 0d |  | 2026-12-15 08:00 | 2026-12-14 16:00 |  | 0 | 1073FS;1074FS;1075FS | 3FS;CT4441_Tren Maya_S_PMG_MEX:206FS;CT4441_S_SDI_MAD_Schedule (TREN MAYA):599FS | -311d | NO
| Future Activity | 0 | 988 | NO | Versão SCADA - Territory M/ Geo T / Alarm | 37d |  | 2026-09-29 08:00 | 2026-11-23 16:00 |  | 90 |  |  | -311d | YES
| Future Activity | 0 | 989 | NO | FAT interno - Territory M/ Geo T / Alarm | 7d |  | 2026-09-29 08:00 | 2026-10-07 16:00 |  | 0 | 960FS | 990FS;2926FS;3354FS | -316d | NO
| Future Activity | 0 | 990 | NO | Relatório de conclusão - FAT 1 - Territory M/ Geo T / Alarm | 3d |  | 2026-10-08 08:00 | 2026-10-13 16:00 | Silva Alexandre | 27 | 989FS | 3FS | -319d | NO
| Future Activity | 0 | 991 | NO | FAT Cliente - Territory M/ Geo T / Alarm | 5d |  | 2026-11-12 08:00 | 2026-11-18 16:00 | Silva Alexandre | 45 | 962FS | 992FS;2928FS | -308d | NO
| Future Activity | 0 | 992 | NO | Relatório de conclusão - FAT 2 - Territory M/ Geo T / Alarm | 2d |  | 2026-11-19 08:00 | 2026-11-23 16:00 | Silva Alexandre | 18 | 991FS | 3123FS | -311d | NO
| Future Activity | 0 | 1101 | NO | Verificações Testes de Campo - SCADA | 17d | 2023-06-15 08:00 | 2026-06-01 08:00 | 2026-06-25 16:00 |  | 36 |  |  | -230d | YES
| Future Activity | 0 | 1102 | NO | Verificação SAT report Tramo 1 - SCADA | 5d | 2026-06-01 08:00 | 2026-06-01 08:00 | 2026-06-09 16:00 | GENERICO - V&V,Pereira Nicolas | 9 | 2FS | 1103FS | -214d | NO
| Future Activity | 0 | 1103 | NO | Verificação SAT report Tramo 2 - SCADA | 3d | 2026-06-01 08:00 | 2026-06-10 08:00 | 2026-06-12 16:00 | GENERICO - V&V,Pereira Nicolas | 9 | 1102FS | 1104FS | -219d | NO
| Future Activity | 0 | 1104 | NO | Verificação SAT report Tramo 3 - SCADA | 3d | 2026-01-02 08:00 | 2026-06-15 08:00 | 2026-06-17 16:00 | GENERICO - V&V,Torres Guilherme | 9 | 1103FS | 1105FS | -315d | NO
| Future Activity | 0 | 1105 | NO | Verificação SAT report Tramo 4 - SCADA | 3d | 2025-08-04 08:00 | 2026-06-18 08:00 | 2026-06-22 16:00 | GENERICO - V&V,Pereira Nicolas | 9 | 1104FS | 1106FS | -320d | NO
| Future Activity | 0 | 1106 | NO | Verificação SAT report Tramo 5 - SCADA | 3d | 2025-11-03 08:00 | 2026-06-23 08:00 | 2026-06-25 16:00 | GENERICO - V&V | 0 | 1105FS | 1112FS | -232d | NO
| Future Activity | 0 | 1107 | NO | V&V report - SCADA | 95d |  | 2026-08-03 08:00 | 2026-12-17 16:00 |  | 162 |  |  | -309d | YES
| Future Activity | 0 | 1108 | NO | V&V report Tramo 1 - SCADA | 5d | 2026-08-03 08:00 | 2026-08-03 08:00 | 2026-08-07 16:00 | GENERICO - V&V,Pereira Nicolas | 45 | 2FS | 3FS;1109FS | -266d | NO
| Future Activity | 0 | 1109 | NO | V&V report Tramo 2 - SCADA | 4d |  | 2026-08-10 08:00 | 2026-08-13 16:00 | GENERICO - V&V,Pereira Nicolas | 36 | 1108FS | 3FS;1110FS | -275d | NO
| Future Activity | 0 | 1110 | NO | V&V report Tramo 3 - SCADA | 3d | 2025-03-06 08:00 | 2026-08-14 08:00 | 2026-08-18 16:00 | GENERICO - V&V,Pereira Nicolas | 27 | 1109FS | 3FS;1111FS | -372d | NO
| Future Activity | 0 | 1111 | NO | V&V report Tramo 4 - SCADA | 3d | 2025-03-06 08:00 | 2026-08-19 08:00 | 2026-08-21 16:00 | GENERICO - V&V,Pereira Nicolas | 27 | 1110FS | 3FS;1112FS | -375d | NO
| Future Activity | 0 | 1112 | NO | V&V report Tramo 5 - SCADA | 3d |  | 2026-12-15 08:00 | 2026-12-17 16:00 | GENERICO - V&V | 27 | 1073FS;1074FS;1075FS;1106FS;1111FS | 3FS | -309d | NO
| Confirmed | 0 | 815 | NO | Revisão DOCs TMS | 72d |  | 2026-01-05 08:00 | 2026-04-22 16:00 |  | 49 |  |  | -20111d | YES
| Confirmed | 98.6864 | 1491 | NO | SCADA | 1452d |  | 2021-06-09 08:00 | 2027-06-14 16:00 |  | 18803.5041 |  |  | -223d | YES
| Confirmed | 98.6171 | 1510 | NO | SCADA Sub System Engineering & Design | 1442d |  | 2021-06-09 08:00 | 2027-05-31 16:00 |  | 11864.2645 |  |  | -209d | YES
| Confirmed | 40 | 1524 | NO | Inputs | 1043d |  | 2021-12-06 08:00 | 2026-04-01 16:00 |  | 0 |  |  | -183d | YES
| Future Activity | 0 | 1526 | NO | Inputs from Customer | 0d |  | 2026-04-02 08:00 | 2026-04-01 16:00 |  | 0 |  |  | -183d | YES
| Future Activity | 0 | 1527 | NO | Tramos 1 a 5 | 0d |  | 2026-04-02 08:00 | 2026-04-01 16:00 |  | 0 |  |  | -183d | YES
| Future Activity | 0 | 1528 | NO | Input - IO list - SCADA TES - V1 - Tramos 1 a 5 | 0d | 2026-04-02 08:00 | 2026-04-02 08:00 | 2026-04-01 16:00 |  | 0 | 2FS | 3032FS | -183d | NO
| Future Activity | 0 | 1529 | NO | Input - IO list - SCADA TEN - V1 - Tramos 1 a 5 | 0d | 2026-04-02 08:00 | 2026-04-02 08:00 | 2026-04-01 16:00 |  | 0 | 2FS | 3033FS | -183d | NO
| Future Activity | 0 | 1530 | NO | Input - IO list - SCADA TSG - V1 - Tramos 1 a 5 | 0d | 2026-04-02 08:00 | 2026-04-02 08:00 | 2026-04-01 16:00 |  | 0 | 2FS | 3034FS | -183d | NO
| Confirmed | 83.0507 | 2767 | NO | SCADA Management | 1282d |  | 2021-11-03 08:00 | 2027-02-26 16:00 |  | 1193.1858 |  |  | -326d | YES
| Confirmed | 0 | 2776 | NO | LE - Suporte UHMI Intern | 113d | 2025-11-03 08:00 | 2025-11-03 08:00 | 2026-04-30 16:00 | Belini Thais,OLIVEIRA JOAO | 113.1858 | 2FS | 3FS |  | NO
| Confirmed | 0 | 2768 | NO | LE - Scada Leader T1 a T7 | 982d | 2023-02-01 08:00 | 2023-02-01 08:00 | 2027-02-26 16:00 | Carvalhal Rogerio,SILVA GERALDO,Viegas Victor | 1080 | 2FS | 3FS | -302d | NO
| Confirmed | 19.5418 | 2777 | NO | SCADA - MXTM | 1559d |  | 2021-06-09 08:00 | 2027-05-31 16:00 |  | 10671.0786 |  |  | -209d | YES
| Confirmed | 0.29215 | 2833 | NO | SCADA Dataprep | 1520d |  | 2021-06-09 08:00 | 2027-04-06 16:00 |  | 10077.0786 |  |  | -154d | YES
| Confirmed | 0 | 3059 | NO | Interface SCADA - TMS | 201d | 2025-07-01 08:00 | 2025-07-01 08:00 | 2026-04-30 16:00 | Pereira Davi | 71.9231 | 2FS | 3FS | -181d | NO
| Confirmed | 0.14508 | 3023 | NO | Inputs | 310d |  | 2025-05-26 08:00 | 2026-07-31 16:00 |  | 433.8 |  |  | -149d | YES
| Future Activity | 0 | 3057 | NO | INPUTS: T6 a T7- CWI + CWE | 0d | 2026-04-01 08:00 | 2026-04-01 08:00 |  |  | 0 | 2FS | 3058FS | -152d | NO
| Future Activity | 0 | 3058 | NO | Análise dos Inputs - T6 a T7- CWI + CWE | 25d |  | 2026-04-01 08:00 | 2026-05-11 16:00 | Oda Robson | 109.8 | 3057FS | 3FS | -154d | NO
| Future Activity | 0 | 3031 | NO | Inputs CWE | 50d |  | 2026-05-25 08:00 | 2026-07-31 16:00 |  | 216 |  |  | -149d | YES
| Future Activity | 0 | 3032 | NO | Análise de Listados - TES - CWE - Estações | 10d | 2026-05-25 08:00 | 2026-05-25 08:00 | 2026-06-09 16:00 | Pereira Davi | 36 | 1528FS | 2936FS;3033SS;3034FS | -208d | NO
| Future Activity | 0 | 3033 | NO | Análise de Listados - TEN - CWE - Estações | 46d |  | 2026-05-25 08:00 | 2026-07-31 16:00 | Oda Robson | 72 | 1529FS;3032SS | 2971FS-15d | -182d | NO
| Future Activity | 0 | 3034 | NO | Análise de Listados - TSG - CWE - Estações | 20d |  | 2026-06-10 08:00 | 2026-07-07 16:00 | Pereira Davi | 108 | 1530FS;3032FS | 3010FS | -125d | NO
| Confirmed | 25 | 3046 | NO | Inputs PLO | 272d |  | 2025-06-02 08:00 | 2026-06-16 16:00 |  | 108 |  |  | -182d | YES
| Future Activity | 0 | 3048 | NO | Análise de Listados - TEN - PLO - Tramo 4 | 10d | 2026-05-04 08:00 | 2026-05-04 08:00 | 2026-05-15 16:00 | Belini Thais | 36 | 2FS | 2986FS;3049FS | -182d | NO
| Future Activity | 0 | 3049 | NO | Análise de Listados - TEN - PLO - Tramo 5 | 10d |  | 2026-05-18 08:00 | 2026-05-29 16:00 | Belini Thais | 36 | 3048FS | 2987FS;3050FS | -178d | NO
| Future Activity | 0 | 3050 | NO | Análise de Listados - TEN - PLO - Tramo 6 | 10d |  | 2026-06-01 08:00 | 2026-06-16 16:00 | GENERICO - ATS Application | 36 | 3049FS | 2986FS;2988FS | -182d | NO
| Confirmed | 53.75 | 2932 | NO | Dataprep TEN/TES/TSG (SubSYS) | 460d |  | 2025-05-28 08:00 | 2027-03-02 16:00 |  | 4472.3556 |  |  | -239d | YES
| Confirmed | 75 | 2933 | NO | Dataprep TES | 460d |  | 2025-05-28 08:00 | 2027-03-02 16:00 |  | 1389 |  |  | -239d | YES
| Future Activity | 0 | 2934 | NO | Dataprep - TES (CWE) | 190d |  | 2026-06-10 08:00 | 2027-03-02 16:00 |  | 1389 |  |  | -183d | YES
| Future Activity | 0 | 2935 | NO | Estações | 190d |  | 2026-06-10 08:00 | 2027-03-02 16:00 |  | 1389 |  |  | -183d | YES
| Future Activity | 0 | 2936 | NO | Dataprep - TES (CWE) - T3 - Estações | 36d |  | 2026-06-10 08:00 | 2026-07-31 16:00 | Belini Thais,OLIVEIRA JOAO | 252 | 3032FS | 2892FS;2937FS;3217FS | -196d | NO
| Future Activity | 0 | 2937 | NO | Dataprep - TES (CWE) - T4 - Estações | 25d |  | 2026-08-03 08:00 | 2026-09-04 16:00 | Pereira Davi | 225 | 2936FS | 2893FS;2938FS;3218FS | -177d | NO
| Future Activity | 0 | 2938 | NO | Dataprep - TES (CWE) - T1 - Estações | 30d |  | 2026-09-08 08:00 | 2026-10-20 16:00 | Pereira Davi | 245 | 2937FS | 2894FS;2939FS;3096FS;3219FS | -176d | NO
| Future Activity | 0 | 2939 | NO | Dataprep - TES (CWE) - T2 - Estações | 25d |  | 2026-10-21 08:00 | 2026-11-26 16:00 | Pereira Davi | 195 | 2938FS | 2895FS;2940FS;3096FS;3220FS | -177d | NO
| Future Activity | 0 | 2940 | NO | Dataprep - TES (CWE) - T5 - Estações | 15d |  | 2026-11-27 08:00 | 2026-12-17 16:00 | Pereira Davi | 118 | 2939FS | 2896FS;2941FS;3221FS | -175d | NO
| Future Activity | 0 | 2941 | NO | Dataprep - TES (CWE) - T6 - Estações | 25d |  | 2026-12-18 08:00 | 2027-01-28 16:00 | Pereira Davi | 195 | 2940FS | 2897FS;2942FS;3222FS | -178d | NO
| Future Activity | 0 | 2942 | NO | Dataprep - TES (CWE) - T7 - Estações | 20d |  | 2027-01-29 08:00 | 2027-03-02 16:00 | Pereira Davi | 159 | 2941FS | 2898FS;2916FS;3223FS | -183d | NO
| Confirmed | 36.25 | 2968 | NO | Dataprep TEN | 410d |  | 2025-06-03 08:00 | 2026-12-28 16:00 |  | 1814.5556 |  |  | -264d | YES
| Future Activity | 0 | 2969 | NO | Dataprep - TEN (CWE) | 121d |  | 2026-07-13 08:00 | 2026-12-28 16:00 |  | 822.5556 |  |  | -145d | YES
| Future Activity | 0 | 2970 | NO | Estações | 121d |  | 2026-07-13 08:00 | 2026-12-28 16:00 |  | 822.5556 |  |  | -145d | YES
| Future Activity | 0 | 2971 | NO | Dataprep - TEN (CWE) - T3 - Estações | 18d |  | 2026-07-13 08:00 | 2026-08-05 16:00 | Oda Robson | 162 | 3033FS-15d | 2864FS;2972FS;3317FS | -182d | NO
| Future Activity | 0 | 2972 | NO | Dataprep - TEN (CWE) - T4 - Estações | 15d |  | 2026-08-06 08:00 | 2026-08-26 16:00 | Oda Robson | 135 | 2971FS | 2865FS;2973FS;3318FS | -147d | NO
| Future Activity | 0 | 2973 | NO | Dataprep - TEN (CWE) - T1 - Estações | 18d |  | 2026-08-27 08:00 | 2026-09-22 16:00 | OLIVEIRA JOAO | 95.5556 | 2972FS | 2866FS;2974FS-2d;3010FS;3319FS | -145d | NO
| Future Activity | 0 | 2974 | NO | Dataprep - TEN (CWE) - T2 - Estações | 30d |  | 2026-09-21 08:00 | 2026-11-03 16:00 | Oda Robson | 135 | 2973FS-2d | 2867FS;2975FS;3320FS | -144d | NO
| Future Activity | 0 | 2975 | NO | Dataprep - TEN (CWE) - T5 - Estações | 9d |  | 2026-11-04 08:00 | 2026-11-16 16:00 | OLIVEIRA JOAO | 81 | 2974FS | 2868FS;2976FS;3321FS | -144d | NO
| Future Activity | 0 | 2976 | NO | Dataprep - TEN (CWE) - T6 - Estações | 15d |  | 2026-11-17 08:00 | 2026-12-08 16:00 | Oda Robson | 115 | 2975FS | 2869FS;2977FS;3322FS | -141d | NO
| Future Activity | 0 | 2977 | NO | Dataprep - TEN (CWE) - T7 - Estações | 12d |  | 2026-12-09 08:00 | 2026-12-28 16:00 | Oda Robson | 99 | 2976FS | 2870FS;3323FS | -145d | NO
| Confirmed | 25 | 2984 | NO | Dataprep - TEN (PLO) | 334d |  | 2025-06-03 08:00 | 2026-09-11 16:00 |  | 528 |  |  | -73d | YES
| Future Activity | 0 | 2986 | NO | Dataprep - TEN (PLO) - T4 | 20d |  | 2026-06-17 08:00 | 2026-07-16 16:00 | GENERICO - ATS Application | 180 | 3048FS;3050FS | 2880FS;2987FS;3332FS | -134d | NO
| Future Activity | 0 | 2987 | NO | Dataprep - TEN (PLO) - T5 | 20d |  | 2026-07-17 08:00 | 2026-08-13 16:00 | GENERICO - ATS Application | 180 | 2986FS;3049FS | 2879FS;2988FS;3334FS | -76d | NO
| Future Activity | 0 | 2988 | NO | Dataprep - TEN (PLO) - T6 | 20d |  | 2026-08-14 08:00 | 2026-09-11 16:00 | GENERICO - ATS Application | 168 | 2987FS;3050FS | 2878FS;2881FS;3333FS | -73d | NO
| Confirmed | 20 | 2989 | NO | Dataprep - TEN (CFE) | 219d |  | 2025-10-13 08:00 | 2026-08-13 16:00 |  | 464 |  |  | -268d | YES
| Confirmed | 20 | 2990 | NO | Subestações | 219d |  | 2025-10-13 08:00 | 2026-08-13 16:00 |  | 464 |  |  | -268d | YES
| Future Activity | 0 | 2992 | NO | Dataprep - TEN (CFE) - T3- Subestações | 15d | 2026-03-23 08:00 | 2026-04-22 08:00 | 2026-05-13 16:00 | Belini Thais,Pereira Davi | 114 | 2860FS;2927FS-10d;3065FS | 2884FS;2993FS;2993FS | -217d | NO
| Future Activity | 0 | 2993 | NO | Dataprep - TEN (CFE) - T4- Subestações | 15d | 2026-05-25 08:00 | 2026-05-25 08:00 | 2026-06-16 16:00 | Belini Thais,Pereira Davi | 80 | 2992FS;2992FS | 2885FS;2994FS | -250d | NO
| Future Activity | 0 | 2994 | NO | Dataprep - TEN (CFE) - T5- Subestações | 15d | 2026-07-01 08:00 | 2026-07-01 08:00 | 2026-07-23 16:00 | Belini Thais,Pereira Davi | 135 | 2993FS | 2886FS;2995FS | -212d | NO
| Future Activity | 0 | 2995 | NO | Dataprep - TEN (CFE) - T6- Subestações | 15d |  | 2026-07-24 08:00 | 2026-08-13 16:00 | Belini Thais,Pereira Davi | 135 | 2994FS | 2884FS;2887FS | -78d | NO
| Confirmed | 50 | 2996 | NO | Dataprep TSG | 458d |  | 2025-05-28 08:00 | 2027-02-26 16:00 |  | 1268.8 |  |  | -308d | YES
| Confirmed | 66.6667 | 2997 | NO | Dataprep - TSG (CWI) | 245d |  | 2025-07-02 08:00 | 2026-06-09 16:00 |  | 206.8 |  |  | -169d | YES
| Confirmed | 33.3333 | 3001 | NO | TyC | 245d |  | 2025-07-02 08:00 | 2026-06-09 16:00 |  | 206.8 |  |  | -236d | YES
| Future Activity | 0 | 3006 | NO | Dataprep - TSG (CWI) - Cocheras de Tulúm | 5d |  | 2026-05-11 08:00 | 2026-05-15 16:00 | Belini Thais,Oda Robson | 49.4 | 1038FS;1496FS | 2842FS;3007FS;3286FS | -234d | NO
| Future Activity | 0 | 3007 | NO | Dataprep - TSG (CWI) - TyC Escárcega | 5d |  | 2026-05-18 08:00 | 2026-05-22 16:00 | Belini Thais,Oda Robson | 49.4 | 3006FS | 2844FS;3003FS;3284FS | -220d | NO
| Future Activity | 0 | 3003 | NO | Dataprep - TSG (CWI) - TyC Chetumal | 5d |  | 2026-05-25 08:00 | 2026-05-29 16:00 | Oda Robson | 45 | 3007FS | 2845FS;3005FS;3285FS | -220d | NO
| Future Activity | 0 | 3005 | NO | Dataprep - TSG (CWI) - Cocheras de Mérida | 5d |  | 2026-06-01 08:00 | 2026-06-09 16:00 | Oda Robson | 63 | 3003FS | 1501FS;2840FS;3022FS;3283FS | -224d | NO
| Future Activity | 0 | 3008 | NO | Dataprep - TSG (CWE) | 113d |  | 2026-09-23 08:00 | 2027-02-26 16:00 |  | 972 |  |  | -308d | YES
| Future Activity | 0 | 3009 | NO | Estações | 113d |  | 2026-09-23 08:00 | 2027-02-26 16:00 |  | 972 |  |  | -308d | YES
| Future Activity | 0 | 3010 | NO | Dataprep - TSG (CWE) - T3- Estações | 18d |  | 2026-09-23 08:00 | 2026-10-19 16:00 | Pereira Davi | 171 | 2973FS;3034FS | 2848FS;3011FS;3090FS;3268FS | -145d | NO
| Future Activity | 0 | 3011 | NO | Dataprep - TSG (CWE) - T4- Estações | 15d |  | 2026-10-20 08:00 | 2026-11-10 16:00 | Pereira Davi | 144 | 3010FS | 2849FS;3012FS;3090FS;3274FS | -144d | NO
| Future Activity | 0 | 3012 | NO | Dataprep - TSG (CWE) - T1- Estações | 18d |  | 2026-11-11 08:00 | 2026-12-07 16:00 | Pereira Davi | 171 | 3011FS | 2850FS;3013FS;3097FS;3273FS | -143d | NO
| Future Activity | 0 | 3013 | NO | Dataprep - TSG (CWE) - T2- Estações | 15d |  | 2026-12-08 08:00 | 2026-12-30 16:00 | OLIVEIRA JOAO | 153 | 3012FS | 2851FS;3014FS;3097FS;3272FS | -145d | NO
| Future Activity | 0 | 3014 | NO | Dataprep - TSG (CWE) - T5- Estações | 9d |  | 2027-01-04 08:00 | 2027-01-14 16:00 | Pereira Davi | 81 | 3013FS | 2852FS;3015FS;3104FS;3271FS | -147d | NO
| Future Activity | 0 | 3015 | NO | Dataprep - TSG (CWE) - T6- Estações | 15d |  | 2027-01-15 08:00 | 2027-02-05 16:00 | Pereira Davi | 144 | 3014FS | 2853FS;3016FS;3111FS;3270FS | -147d | NO
| Future Activity | 0 | 3016 | NO | Dataprep - TSG (CWE) - T7- Estações | 12d |  | 2027-02-11 08:00 | 2027-02-26 16:00 | GENERICO - ATS Application | 108 | 3015FS | 2854FS;3111FS;3269FS | -150d | NO
| Confirmed | 33.3333 | 3019 | NO | Dataprep - TSG (ISM) | 171d |  | 2025-10-28 08:00 | 2026-06-23 16:00 |  | 90 |  |  | -95d | YES
| Future Activity | 0 | 3022 | NO | Dataprep - TSG (ISM) - T2 a T4 - Casetas, Estações e TyC | 4d |  | 2026-06-10 08:00 | 2026-06-15 16:00 | Pereira Davi | 36 | 1498FS;3005FS | 2859FS;3021FS;3262FS |  | NO
| Future Activity | 0 | 3021 | NO | Dataprep - TSG (ISM) - T5 a T7 - Casetas, Estações e TyC | 6d |  | 2026-06-16 08:00 | 2026-06-23 16:00 | Oda Robson | 54 | 3022FS | 2859FS;3265FS | -95d | NO
| Confirmed | 40.5556 | 2834 | NO | Data interface TEN/TES/TSG (SubSYS) | 1511d |  | 2021-06-09 08:00 | 2027-03-24 16:00 |  | 4264 |  |  | -182d | YES
| Confirmed | 66.6667 | 2889 | NO | DI com End de Campo TES | 475d |  | 2025-05-28 08:00 | 2027-03-23 16:00 |  | 562 |  |  | -182d | YES
| Future Activity | 0 | 2890 | NO | DI com End. de Campo - TES (CWE) | 158d |  | 2026-08-03 08:00 | 2027-03-10 16:00 |  | 481 |  |  | -169d | YES
| Future Activity | 0 | 2891 | NO | Estações | 158d |  | 2026-08-03 08:00 | 2027-03-10 16:00 |  | 481 |  |  | -169d | YES
| Future Activity | 0 | 2892 | NO | DI com End. de Campo - TES (CWE) - T3 - Estações | 9d |  | 2026-08-03 08:00 | 2026-08-13 16:00 | Pereira Davi | 81 | 2936FS | 2783FS;2893FS | -23d | NO
| Future Activity | 0 | 2893 | NO | DI com End. de Campo - TES (CWE) - T4 - Estações | 8d |  | 2026-09-08 08:00 | 2026-09-17 16:00 | Pereira Davi | 72 | 2892FS;2937FS | 2783FS;2894FS | -48d | NO
| Future Activity | 0 | 2894 | NO | DI com End. de Campo - TES (CWE) - T1 - Estações | 9d |  | 2026-10-21 08:00 | 2026-11-03 16:00 | Pereira Davi | 72 | 2893FS;2938FS | 2790FS;2895FS | -82d | NO
| Future Activity | 0 | 2895 | NO | DI com End. de Campo - TES (CWE) - T2 - Estações | 8d |  | 2026-11-27 08:00 | 2026-12-08 16:00 | Pereira Davi | 63 | 2894FS;2939FS | 2790FS;2896FS | -105d | NO
| Future Activity | 0 | 2896 | NO | DI com End. de Campo - TES (CWE) - T5 - Estações | 5d |  | 2026-12-18 08:00 | 2026-12-28 16:00 | Pereira Davi | 40 | 2895FS;2940FS | 2797FS;2897FS | -118d | NO
| Future Activity | 0 | 2897 | NO | DI com End. de Campo - TES (CWE) - T6 - Estações | 8d |  | 2027-01-29 08:00 | 2027-02-12 16:00 | Pereira Davi | 99 | 2896FS;2941FS | 2804FS;2898FS | -151d | NO
| Future Activity | 0 | 2898 | NO | DI com End. de Campo - TES (CWE) - T7 - Estações | 6d |  | 2027-03-03 08:00 | 2027-03-10 16:00 | Pereira Davi | 54 | 2897FS;2942FS | 2804FS;2904FS | -169d | NO
| Confirmed | 83.3333 | 2899 | NO | DI com End. de Campo - TES (CWI) | 119d |  | 2025-10-22 08:00 | 2026-04-06 16:00 |  | 63 |  |  | -126d | YES
| Confirmed | 66.6667 | 2903 | NO | TyC | 103d |  | 2025-11-13 08:00 | 2026-04-06 16:00 |  | 63 |  |  | -187d | YES
| Future Activity | 0 | 2907 | NO | DI com End. de Campo - TES (CWI) - TyC Escárcega | 3d |  | 2026-03-13 08:00 | 2026-03-17 16:00 | Belini Thais | 27 | 1049FS;2906FS;2930FS;2952FS | 2908FS | -168d | NO
| Future Activity | 0 | 2908 | NO | DI com End. de Campo - TES (CWI) - TyC Chetumal | 3d | 2026-04-01 08:00 | 2026-04-01 08:00 | 2026-04-06 16:00 | Pereira Davi | 36 | 2907FS;2953FS | 1494FS;2916FS;3002FS | -187d | NO
| Confirmed | 83.3333 | 2910 | NO | DI com End. de Campo - TES (CNS) | 466d |  | 2025-06-10 08:00 | 2027-03-23 16:00 |  | 18 |  |  | -627d | YES
| Confirmed | 50 | 2915 | NO | Estações | 462d |  | 2025-06-16 08:00 | 2027-03-23 16:00 |  | 18 |  |  | -627d | YES
| Future Activity | 0 | 2916 | NO | DI com End. de Campo - TES (CNS) - T1 a T7 - Estações | 15d |  | 2027-03-03 08:00 | 2027-03-23 16:00 | Pereira Davi | 18 | 2845FS;2908FS;2942FS;2961FS | 3FS | -627d | NO
| Confirmed | 30 | 2861 | NO | DI com End de Campo TEN | 1486d |  | 2021-06-09 08:00 | 2027-02-17 16:00 |  | 2271 |  |  | -147d | YES
| Future Activity | 0 | 2862 | NO | DI com End. de Campo - TEN (CWE) | 113d |  | 2026-09-14 08:00 | 2027-02-17 16:00 |  | 842 |  |  | -147d | YES
| Future Activity | 0 | 2863 | NO | Estações | 113d |  | 2026-09-14 08:00 | 2027-02-17 16:00 |  | 842 |  |  | -147d | YES
| Future Activity | 0 | 2864 | NO | DI com End. de Campo - TEN (CWE) - T3 - Estações | 18d |  | 2026-09-14 08:00 | 2026-10-07 16:00 | Belini Thais | 162 | 2884FS;2971FS | 2781FS;2865FS;3339FS | -139d | NO
| Future Activity | 0 | 2865 | NO | DI com End. de Campo - TEN (CWE) - T4 - Estações | 15d |  | 2026-10-08 08:00 | 2026-10-29 16:00 | Oda Robson | 80 | 2864FS;2972FS | 3FS;2781FS;2866FS;3340FS | -136d | NO
| Future Activity | 0 | 2866 | NO | DI com End. de Campo - TEN (CWE) - T1 - Estações | 18d |  | 2026-10-30 08:00 | 2026-11-26 16:00 | Oda Robson | 147 | 2865FS;2973FS | 3FS;2788FS;2867FS;3341FS | -136d | NO
| Future Activity | 0 | 2867 | NO | DI com End. de Campo - TEN (CWE) - T2 - Estações | 15d |  | 2026-11-27 08:00 | 2026-12-17 16:00 | Oda Robson | 120 | 2866FS;2974FS | 3FS;2788FS;2868FS;3342FS | -136d | NO
| Future Activity | 0 | 2868 | NO | DI com End. de Campo - TEN (CWE) - T5 - Estações | 9d |  | 2026-12-18 08:00 | 2027-01-05 16:00 | Oda Robson | 72 | 2867FS;2975FS | 3FS;2795FS;2869FS;3343FS | -144d | NO
| Future Activity | 0 | 2869 | NO | DI com End. de Campo - TEN (CWE) - T6 - Estações | 15d |  | 2027-01-06 08:00 | 2027-01-27 16:00 | Oda Robson | 126 | 2868FS;2976FS | 3FS;2802FS;2870FS;3344FS | -145d | NO
| Future Activity | 0 | 2870 | NO | DI com End. de Campo - TEN (CWE) - T7 - Estações | 12d |  | 2027-01-28 08:00 | 2027-02-17 16:00 | Oda Robson | 135 | 2869FS;2977FS | 2802FS;3345FS | -147d | NO
| Future Activity | 0 | 2877 | NO | DI com End. de Campo - TEN (PLO) | 67d |  | 2026-09-14 08:00 | 2026-12-15 16:00 |  | 497 |  |  | -231d | YES
| Future Activity | 0 | 2878 | NO | DI com End. de Campo - TEN (PLO) - T3 | 4d |  | 2026-09-14 08:00 | 2026-09-17 16:00 | GENERICO - ATS Application | 36 | 2985FS;2988FS | 2880FS | -234d | NO
| Future Activity | 0 | 2880 | NO | DI com End. de Campo - TEN (PLO) - T4 | 20d |  | 2026-09-18 08:00 | 2026-10-16 16:00 | GENERICO - ATS Application | 140 | 2878FS;2986FS | 2879FS | -232d | NO
| Future Activity | 0 | 2879 | NO | DI com End. de Campo - TEN (PLO) - T5 | 20d |  | 2026-10-19 08:00 | 2026-11-16 16:00 | GENERICO - ATS Application | 160 | 2880FS;2987FS | 2881FS | -235d | NO
| Future Activity | 0 | 2881 | NO | DI com End. de Campo - TEN (PLO) - T6 | 20d |  | 2026-11-17 08:00 | 2026-12-15 16:00 | GENERICO - ATS Application | 161 | 2879FS;2988FS | 3FS | -231d | NO
| Confirmed | 20 | 2882 | NO | DI com End. de Campo - TEN (CFE) | 1471d |  | 2021-06-09 08:00 | 2027-01-27 16:00 |  | 932 |  |  | -244d | YES
| Confirmed | 20 | 2883 | NO | Subestações | 1471d |  | 2021-06-09 08:00 | 2027-01-27 16:00 |  | 932 |  |  | -244d | YES
| Future Activity | 0 | 2884 | NO | DI com End. de Campo - TEN (CFE) - T3- Subestações | 20d |  | 2026-08-14 08:00 | 2026-09-11 16:00 | Belini Thais | 189 | 2992FS;2995FS | 2864FS;2885FS | -241d | NO
| Future Activity | 0 | 2885 | NO | DI com End. de Campo - TEN (CFE) - T4- Subestações | 30d |  | 2026-09-14 08:00 | 2026-10-26 16:00 | OLIVEIRA JOAO | 259 | 2884FS;2993FS | 2886FS | -241d | NO
| Future Activity | 0 | 2886 | NO | DI com End. de Campo - TEN (CFE) - T5- Subestações | 30d |  | 2026-10-27 08:00 | 2026-12-09 16:00 | Oda Robson | 235 | 2885FS;2994FS | 2887FS | -240d | NO
| Future Activity | 0 | 2887 | NO | DI com End. de Campo - TEN (CFE) - T6- Subestações | 30d |  | 2026-12-10 08:00 | 2027-01-27 16:00 | Pereira Davi | 249 | 2886FS;2995FS | 3FS | -244d | NO
| Confirmed | 25 | 2835 | NO | DI com End de Campo TSG | 475d |  | 2025-05-29 08:00 | 2027-03-24 16:00 |  | 1431 |  |  | -182d | YES
| Confirmed | 50 | 2836 | NO | DI com End. de Campo - TSG (CWI) | 165d |  | 2025-11-28 08:00 | 2026-07-16 16:00 |  | 189 |  |  | -175d | YES
| Future Activity | 0 | 2839 | NO | TyC | 22d |  | 2026-06-17 08:00 | 2026-07-16 16:00 |  | 189 |  |  | -248d | YES
| Future Activity | 0 | 2840 | NO | DI com End. de Campo - TSG (CWI) - Cochera Campeche | 5d |  | 2026-06-17 08:00 | 2026-06-23 16:00 | Oda Robson | 45 | 1501FS;3004FS;3005FS | 2841FS | -238d | NO
| Future Activity | 0 | 2841 | NO | DI com End. de Campo - TSG (CWI) - Cocheras de Mérida | 3d |  | 2026-06-24 08:00 | 2026-06-26 16:00 | Oda Robson | 27 | 2840FS | 2842FS;2843FS | -239d | NO
| Future Activity | 0 | 2843 | NO | DI com End. de Campo - TSG (CWI) - TyC Cancún | 3d |  | 2026-06-29 08:00 | 2026-07-01 16:00 | OLIVEIRA JOAO | 27 | 2841FS;3002FS | 2842FS | -243d | NO
| Future Activity | 0 | 2842 | NO | DI com End. de Campo - TSG (CWI) - Cocheras de Tulúm | 3d |  | 2026-07-02 08:00 | 2026-07-06 16:00 | Oda Robson | 27 | 2841FS;2843FS;3006FS | 2844FS;3304FS | -244d | NO
| Future Activity | 0 | 2844 | NO | DI com End. de Campo - TSG (CWI) - TyC Escárcega | 3d |  | 2026-07-07 08:00 | 2026-07-13 16:00 | Oda Robson | 45 | 2842FS;3007FS | 2845FS | -249d | NO
| Future Activity | 0 | 2845 | NO | DI com End. de Campo - TSG (CWI) - TyC Chetumal | 3d |  | 2026-07-14 08:00 | 2026-07-16 16:00 | Oda Robson | 18 | 2844FS;3003FS | 2916FS | -248d | NO
| Future Activity | 0 | 2846 | NO | DI com End. de Campo - TSG (CWE) | 112d |  | 2026-10-20 08:00 | 2027-03-24 16:00 |  | 1008 |  |  | -182d | YES
| Future Activity | 0 | 2847 | NO | Estações | 112d |  | 2026-10-20 08:00 | 2027-03-24 16:00 |  | 1008 |  |  | -182d | YES
| Future Activity | 0 | 2848 | NO | DI com End. de Campo - TSG (CWE) - T3- Estações | 18d |  | 2026-10-20 08:00 | 2026-11-13 16:00 | Pereira Davi | 171 | 3010FS | 2785FS;2849FS | -176d | NO
| Future Activity | 0 | 2849 | NO | DI com End. de Campo - TSG (CWE) - T4- Estações | 15d |  | 2026-11-16 08:00 | 2026-12-07 16:00 | Pereira Davi | 144 | 2848FS;3011FS | 2785FS;2850FS;3297FS+5d | -175d | NO
| Future Activity | 0 | 2850 | NO | DI com End. de Campo - TSG (CWE) - T1- Estações | 18d |  | 2026-12-08 08:00 | 2027-01-06 16:00 | Pereira Davi | 198 | 2849FS;3012FS | 2792FS;2851FS | -177d | NO
| Future Activity | 0 | 2851 | NO | DI com End. de Campo - TSG (CWE) - T2- Estações | 15d |  | 2027-01-07 08:00 | 2027-01-28 16:00 | Pereira Davi | 144 | 2850FS;3013FS | 2792FS;2852FS | -178d | NO
| Future Activity | 0 | 2852 | NO | DI com End. de Campo - TSG (CWE) - T5- Estações | 9d |  | 2027-01-29 08:00 | 2027-02-15 16:00 | Pereira Davi | 108 | 2851FS;3014FS | 2799FS;2853FS | -185d | NO
| Future Activity | 0 | 2853 | NO | DI com End. de Campo - TSG (CWE) - T6- Estações | 15d |  | 2027-02-16 08:00 | 2027-03-08 16:00 | Pereira Davi | 135 | 1501FS;2852FS;3015FS | 2806FS;2854FS | -185d | NO
| Future Activity | 0 | 2854 | NO | DI com End. de Campo - TSG (CWE) - T7- Estações | 12d |  | 2027-03-09 08:00 | 2027-03-24 16:00 | Pereira Davi | 108 | 1501FS;2853FS;3016FS | 3FS;2806FS | -182d | NO
| Confirmed | 50 | 2855 | NO | DI com End. de Campo - TSG (DAU) | 375d |  | 2025-05-29 08:00 | 2026-11-04 16:00 |  | 180 |  |  | -334d | YES
| Future Activity | 0 | 2857 | NO | DI Desenvovimento API S2K-Phoenix | 20d |  | 2026-10-06 08:00 | 2026-11-04 16:00 | Silva Alexandre | 180 | 961FS | 3291FS | -334d | NO
| Future Activity | 0 | 2858 | NO | DI com End. de Campo - TSG (ISM) | 6d |  | 2026-06-24 08:00 | 2026-07-01 16:00 |  | 54 |  |  | -259d | YES
| Future Activity | 0 | 2859 | NO | DI com End. de Campo - TSG (ISM) - T1 a T4 - Casetas, Estações e TyC | 4d |  | 2026-06-24 08:00 | 2026-06-29 16:00 | OLIVEIRA JOAO | 36 | 3021FS;3022FS | 2860FS |  | NO
| Future Activity | 0 | 2860 | NO | DI com End. de Campo - TSG (ISM) - T5 a T7 - Casetas, Estações e TyC | 2d |  | 2026-06-30 08:00 | 2026-07-01 16:00 | OLIVEIRA JOAO | 18 | 2859FS | 2992FS | -259d | NO
| Confirmed | 30.7692 | 3067 | NO | RLN & OUTPUTs TEN/TES/TSG | 343d |  | 2025-12-12 08:00 | 2027-04-06 16:00 |  | 216 |  |  | -154d | YES
| Future Activity | 0 | 3084 | NO | OUTPUTs RELEASE TO V&V - CWE | 136d |  | 2026-09-29 08:00 | 2027-04-06 16:00 |  | 162 |  |  | -162d | YES
| Future Activity | 0 | 3085 | NO | OUTPUT: SCADA RELEASE NOTES V&V - (TEN/TES/TSG) CWE (T3/T4) | 55d |  | 2026-09-29 08:00 | 2026-12-17 16:00 |  | 36 |  |  | -20350d | YES
| Future Activity | 0 | 3086 | NO | OUTPUT: SCADA pós Testes Internos - TEN CWE (T3/T4) | 0d |  | 2026-11-10 08:00 | 2026-11-09 16:00 |  | 0 | 3339FS;3340FS | 3087FS |  | NO
| Future Activity | 0 | 3087 | NO | RLN V&V - TEN CWE (T3/T4) | 2d |  | 2026-11-10 08:00 | 2026-11-11 16:00 | Oda Robson | 18 | 3086FS | 973FS |  | NO
| Future Activity | 0 | 3088 | NO | OUTPUT: SCADA pós Testes Internos - TES CWE (T3/T4) | 0d |  | 2026-09-29 08:00 | 2026-09-28 16:00 |  | 0 | 3217FS;3218FS;3241FS;3242FS | 3089FS |  | NO
| Future Activity | 0 | 3089 | NO | RLN V&V - TES CWE (T3/T4) | 1d |  | 2026-09-29 08:00 | 2026-09-29 16:00 | Oda Robson | 9 | 3088FS | 974FS;3090FS |  | NO
| Future Activity | 0 | 3090 | NO | OUTPUT: SCADA pós Testes Internos - TSG CWE (T3/T4) | 0d |  | 2026-12-17 08:00 |  |  | 0 | 3010FS;3011FS;3089FS;3296FS;3297FS | 3091FS |  | NO
| Future Activity | 0 | 3091 | NO | RLN V&V - TSG CWE (T3/T4) | 1d |  | 2026-12-17 08:00 | 2026-12-17 16:00 | Oda Robson | 9 | 3090FS | 975FS |  | NO
| Future Activity | 0 | 3092 | NO | OUTPUT: SCADA RELEASE NOTES V&V - (TEN/TES/TSG) CWE (T1/T2) | 33d |  | 2026-12-18 08:00 | 2027-02-12 16:00 |  | 54 |  |  | -20407d | YES
| Future Activity | 0 | 3093 | NO | OUTPUT: SCADA pós Testes Internos - TEN CWE (T1/T2) | 0d |  | 2026-12-30 08:00 | 2026-12-29 16:00 |  | 0 | 3341FS;3342FS | 3094FS | -74d | NO
| Future Activity | 0 | 3094 | NO | RLN V&V - TEN CWE (T1/T2) | 2d |  | 2026-12-30 08:00 | 2027-01-04 16:00 | Oda Robson | 36 | 3093FS | 978FS | -76d | NO
| Future Activity | 0 | 3095 | NO | OUTPUT: SCADA pós Testes Internos - TES CWE (T1/T2) | 0d |  | 2026-12-18 08:00 | 2026-12-17 16:00 |  | 0 | 3219FS;3220FS;3243FS;3244FS | 3096FS | -85d | NO
| Future Activity | 0 | 3096 | NO | RLN V&V - TES CWE (T1/T2) | 1d |  | 2026-12-18 08:00 | 2026-12-18 16:00 | Oda Robson | 9 | 2938FS;2939FS;3095FS | 979FS;3097FS | -85d | NO
| Future Activity | 0 | 3097 | NO | OUTPUT: SCADA pós Testes Internos - TSG CWE (T1/T2) | 0d |  | 2027-02-12 08:00 |  |  | 0 | 3012FS;3013FS;3096FS;3298FS;3299FS | 3098FS | -109d | NO
| Future Activity | 0 | 3098 | NO | RLN V&V - TSG CWE (T1/T2) | 1d |  | 2027-02-12 08:00 | 2027-02-12 16:00 | Oda Robson | 9 | 3097FS | 980FS | -109d | NO
| Future Activity | 0 | 3099 | NO | OUTPUT: SCADA RELEASE NOTES V&V - (TEN/TES/TSG) CWE (T5) | 30d |  | 2027-01-08 08:00 | 2027-02-24 16:00 |  | 36 |  |  | -20419d | YES
| Future Activity | 0 | 3100 | NO | OUTPUT: SCADA pós Testes Internos - TEN CWE (T5) | 0d |  | 2027-01-14 08:00 | 2027-01-13 16:00 |  | 0 | 3343FS | 3101FS |  | NO
| Future Activity | 0 | 3101 | NO | RLN V&V - TEN CWE (T5) | 2d |  | 2027-01-14 08:00 | 2027-01-15 16:00 | Oda Robson | 18 | 3100FS | 978FS |  | NO
| Future Activity | 0 | 3102 | NO | OUTPUT: SCADA pós Testes Internos - TES CWE (T5) | 0d |  | 2027-01-08 08:00 | 2027-01-07 16:00 |  | 0 | 3221FS;3245FS | 3103FS |  | NO
| Future Activity | 0 | 3103 | NO | RLN V&V - TES CWE (T5) | 1d |  | 2027-01-08 08:00 | 2027-01-08 16:00 | Oda Robson | 9 | 3102FS | 979FS;983FS;3104FS |  | NO
| Future Activity | 0 | 3104 | NO | OUTPUT: SCADA pós Testes Internos - TSG CWE (T5) | 0d |  | 2027-02-24 08:00 |  |  | 0 | 3014FS;3103FS;3300FS | 3105FS |  | NO
| Future Activity | 0 | 3105 | NO | RLN V&V - TSG CWE (T5) | 1d |  | 2027-02-24 08:00 | 2027-02-24 16:00 | Oda Robson | 9 | 3104FS | 980FS;985FS |  | NO
| Future Activity | 0 | 3106 | NO | OUTPUT: SCADA RELEASE NOTES V&V - (TEN/TES/TSG) CWE (T6/T7) | 27d |  | 2027-02-26 08:00 | 2027-04-06 16:00 |  | 36 |  |  | -20460d | YES
| Future Activity | 0 | 3107 | NO | OUTPUT: SCADA pós Testes Internos - TEN CWE (T6/T7) | 0d |  | 2027-02-26 08:00 | 2027-02-25 16:00 |  | 0 | 3344FS;3345FS | 3108FS |  | NO
| Future Activity | 0 | 3108 | NO | RLN V&V - TEN CWE (T6/T7) | 2d |  | 2027-02-26 08:00 | 2027-03-01 16:00 | Oda Robson | 18 | 3107FS |  |  | NO
| Future Activity | 0 | 3109 | NO | OUTPUT: SCADA pós Testes Internos - TES CWE (T6/T7) | 0d |  | 2027-03-20 08:00 | 2027-03-19 16:00 |  | 0 | 3222FS;3223FS;3246FS;3247FS | 3110FS |  | NO
| Future Activity | 0 | 3110 | NO | RLN V&V - TES CWE (T6/T7) | 1d |  | 2027-03-22 08:00 | 2027-03-22 16:00 | Oda Robson | 9 | 3109FS | 984FS;3111FS |  | NO
| Future Activity | 0 | 3111 | NO | OUTPUT: SCADA pós Testes Internos - TSG CWE (T6/T7) | 0d |  | 2027-04-06 08:00 |  |  | 0 | 3015FS;3016FS;3110FS;3301FS;3302FS | 3112FS |  | NO
| Future Activity | 0 | 3112 | NO | RLN V&V - TSG CWE (T6/T7) | 1d |  | 2027-04-06 08:00 | 2027-04-06 16:00 | Oda Robson | 9 | 3111FS |  |  | NO
| Confirmed | 61.5385 | 3068 | NO | OUTPUTs CWI | 62d |  | 2025-12-12 08:00 | 2026-03-09 16:00 |  | 54 |  |  | -47d | YES
| Confirmed | 66.6667 | 3077 | NO | FAT | 43d |  | 2026-01-08 08:00 | 2026-03-09 16:00 |  | 18 |  |  | -20067d | YES
| Future Activity | 0 | 3082 | NO | OUTPUT: SCADA pós Testes Internos - TEN OCS | 0d |  | 2026-03-06 08:00 | 2026-03-05 16:00 |  | 0 | 3336FS | 3083FS |  | NO
| Future Activity | 0 | 3083 | NO | RLN V&V - TEN OCS | 2d |  | 2026-03-06 08:00 | 2026-03-09 16:00 | Oda Robson | 18 | 3082FS | 3FS |  | NO
| Confirmed | 57.1429 | 3069 | NO | Demo | 59d |  | 2025-12-12 08:00 | 2026-03-04 16:00 |  | 36 |  |  | -20062d | YES
| Future Activity | 0 | 3073 | NO | OUTPUT: SCADA pós Testes Internos - TEN - DEMO | 0d |  | 2026-03-03 08:00 | 2026-03-02 16:00 |  | 0 | 3350FS | 953FS;3074SS |  | NO
| Future Activity | 0 | 3074 | NO | DEMO RLN V&V - TEN CFE | 2d |  | 2026-03-03 08:00 | 2026-03-04 16:00 | Oda Robson | 18 | 3073SS | 1041FS |  | NO
| Future Activity | 0 | 3075 | NO | RLN V&V - Pós correções V&V - TES/TSG - CWI DEMO | 2d |  | 2026-03-02 08:00 | 2026-03-03 16:00 | Oda Robson | 18 | 2929FS;2930FS;2931FS;3238FS;3311FS;3313FS | 957SS |  | NO
| Confirmed | 66.6667 | 3060 | NO | Configurações e integrações - GAPs | 216d |  | 2025-06-20 08:00 | 2026-04-17 16:00 |  | 151 |  |  | -112d | YES
| Future Activity | 0 | 3064 | NO | Configuração e Integração - Active Directory | 12d | 2026-03-02 08:00 | 2026-03-02 08:00 | 2026-03-17 16:00 | Belini Thais,Oda Robson | 106 | 3079FS | 1496FS;3183FS | -137d | NO
| Future Activity | 0 | 3065 | NO | Configuração e Integração - Territory Management | 5d | 2026-04-13 08:00 | 2026-04-13 08:00 | 2026-04-17 16:00 | Pereira Davi | 45 | 2FS | 2992FS;3066FS | -192d | NO
| Confirmed | 25 | 2923 | NO | Correções | 211d |  | 2026-01-29 08:00 | 2026-11-19 16:00 |  | 468 |  |  | -308d | YES
| Future Activity | 0 | 2931 | NO | Correções pós V&V CRs - TEN CFE CWI - ATS APP DEMO | 7d |  | 2026-03-11 08:00 | 2026-03-19 16:00 | Pereira Davi | 63 | 1041FS | 3075FS |  | NO
| Future Activity | 0 | 2924 | NO | Correções pós V&V CRs - TEN CWI - ATS APP | 15d | 2026-08-03 08:00 | 2026-08-03 08:00 | 2026-08-21 16:00 | Oda Robson | 135 | 1041SS+13d | 1034FS |  | NO
| Future Activity | 0 | 2925 | NO | Correções pós V&V CRs - TES CWI - ATS APP | 15d |  | 2026-03-18 08:00 | 2026-04-08 16:00 | Oda Robson,Pereira Davi | 118.5 | 1040SS+5d | 956FS |  | NO
| Future Activity | 0 | 2927 | NO | Correções pós V&V CRs - TSG CWI - ATS APP | 14d |  | 2026-03-18 08:00 | 2026-04-07 16:00 | Oda Robson,Pereira Davi | 133.5 | 1050SS+5d | 956FS;1496FS;2992FS-10d |  | NO
| Future Activity | 0 | 2926 | NO | Correções pós V&V - GAPs - DEMO3 - Interna | 1d |  | 2026-10-08 08:00 | 2026-10-08 16:00 | Oda Robson | 9 | 989FS | 3FS | -316d | NO
| Future Activity | 0 | 2928 | NO | Correções pós V&V - GAPs - DEMO3 - Cliente | 1d |  | 2026-11-19 08:00 | 2026-11-19 16:00 | Oda Robson | 9 | 991FS | 3FS | -308d | NO
| Confirmed | 58.3333 | 2778 | NO | Testes de Integração | 369d |  | 2025-11-03 08:00 | 2027-04-01 16:00 |  | 594 |  |  | -183d | YES
| Future Activity | 0 | 2779 | NO | Testes de Integração - CWE | 134d |  | 2026-09-18 08:00 | 2027-03-24 16:00 |  | 540 |  |  | -20447d | YES
| Future Activity | 0 | 2780 | NO | TESTES INTERNOS - (TEN/TES/TSG) - CWE (T3/T4) | 59d |  | 2026-09-18 08:00 | 2026-12-14 16:00 |  | 144 |  |  | -20347d | YES
| Future Activity | 0 | 2781 | NO | OUTPUT p/Testes Internos - TEN - CWE (T3/T4) | 0d |  | 2026-10-30 08:00 | 2026-10-29 16:00 |  | 0 | 2864FS;2865FS;3317FS;3318FS | 2782FS | -36d | NO
| Future Activity | 0 | 2782 | NO | Testes DEMO4 - Internas - TEN - CWE (T3/T4) | 5d |  | 2026-10-30 08:00 | 2026-11-06 16:00 | GENERICO - ATS Application | 54 | 2781FS | 3339FS;3340FS | -37d | NO
| Future Activity | 0 | 2783 | NO | OUTPUT p/Testes Internos - TES - CWE (T3/T4) | 0d |  | 2026-09-18 08:00 | 2026-09-17 16:00 |  | 0 | 2892FS;2893FS;3217FS;3218FS | 2784FS | 5d | NO
| Future Activity | 0 | 2784 | NO | Testes DEMO4 - Internas - TES - CWE (T3/T4) | 5d |  | 2026-09-18 08:00 | 2026-09-24 16:00 | GENERICO - ATS Application | 45 | 2783FS | 3241FS;3242FS | 5d | NO
| Future Activity | 0 | 2785 | NO | OUTPUT p/Testes Internos - TSG - CWE (T3/T4) | 0d |  | 2026-12-08 08:00 | 2026-12-07 16:00 |  | 0 | 2848FS;2849FS;3262FS;3264FS | 2786FS | -75d | NO
| Future Activity | 0 | 2786 | NO | Testes DEMO4 - Internas - TSG - CWE (T3/T4) | 5d |  | 2026-12-08 08:00 | 2026-12-14 16:00 | GENERICO - ATS Application | 45 | 2785FS | 3296FS;3297FS | -75d | NO
| Future Activity | 0 | 2787 | NO | TESTES INTERNOS - TEN - CWE (T1/T2) | 37d |  | 2026-12-09 08:00 | 2027-02-04 16:00 |  | 153 |  |  | -20399d | YES
| Future Activity | 0 | 2788 | NO | OUTPUT p/Testes Internos - TEN - CWE (T1/T2) | 0d |  | 2026-12-18 08:00 | 2026-12-17 16:00 |  | 0 | 2866FS;2867FS;3319FS;3320FS | 2789FS |  | NO
| Future Activity | 0 | 2789 | NO | Testes DEMO4 - Internas - TEN - CWE (T1/T2) | 5d |  | 2026-12-18 08:00 | 2026-12-28 16:00 | GENERICO - ATS Application | 63 | 2788FS | 3341FS;3342FS |  | NO
| Future Activity | 0 | 2790 | NO | OUTPUT p/Testes Internos - TES - CWE (T1/T2) | 0d |  | 2026-12-09 08:00 | 2026-12-08 16:00 |  | 0 | 2894FS;2895FS;3219FS;3220FS | 2791FS |  | NO
| Future Activity | 0 | 2791 | NO | Testes DEMO4 - Internas - TES - CWE (T1/T2) | 5d |  | 2026-12-09 08:00 | 2026-12-15 16:00 | GENERICO - ATS Application | 45 | 2790FS | 3243FS;3244FS |  | NO
| Future Activity | 0 | 2792 | NO | OUTPUT p/Testes Internos - TSG - CWE (T1/T2) | 0d |  | 2027-01-29 08:00 | 2027-01-28 16:00 |  | 0 | 2850FS;2851FS;3262FS;3264FS | 2793FS |  | NO
| Future Activity | 0 | 2793 | NO | Testes DEMO4 - Internas - TSG - CWE (T1/T2) | 5d |  | 2027-01-29 08:00 | 2027-02-04 16:00 | GENERICO - ATS Application | 45 | 2792FS | 3298FS;3299FS |  | NO
| Future Activity | 0 | 2794 | NO | TESTES INTERNOS - TEN - CWE (T5) | 34d |  | 2026-12-29 08:00 | 2027-02-22 16:00 |  | 153 |  |  | -20417d | YES
| Future Activity | 0 | 2795 | NO | OUTPUT p/Testes Internos - TEN - CWE (T5) | 0d |  | 2027-01-06 08:00 | 2027-01-05 16:00 |  | 0 | 2868FS;3321FS | 2796FS |  | NO
| Future Activity | 0 | 2796 | NO | Testes DEMO4 - Internas - TEN - CWE (T5) | 5d |  | 2027-01-06 08:00 | 2027-01-12 16:00 | GENERICO - ATS Application | 45 | 2795FS | 3343FS |  | NO
| Future Activity | 0 | 2797 | NO | OUTPUT p/Testes Internos - TES - CWE (T5) | 0d |  | 2026-12-29 08:00 | 2026-12-28 16:00 |  | 0 | 2896FS;3221FS | 2798FS |  | NO
| Future Activity | 0 | 2798 | NO | Testes DEMO4 - Internas - TES - CWE (T5) | 5d |  | 2026-12-29 08:00 | 2027-01-06 16:00 | GENERICO - ATS Application | 63 | 2797FS | 3245FS |  | NO
| Future Activity | 0 | 2799 | NO | OUTPUT p/Testes Internos - TSG - CWE (T5) | 0d |  | 2027-02-16 08:00 | 2027-02-15 16:00 |  | 0 | 2852FS;3263FS | 2800FS |  | NO
| Future Activity | 0 | 2800 | NO | Testes DEMO4 - Internas - TSG - CWE (T5) | 5d |  | 2027-02-16 08:00 | 2027-02-22 16:00 | GENERICO - ATS Application | 45 | 2799FS | 3300FS |  | NO
| Future Activity | 0 | 2801 | NO | TESTES INTERNOS - TEN - CWE (T6/T7) | 25d |  | 2027-02-18 08:00 | 2027-03-24 16:00 |  | 90 |  |  | -20447d | YES
| Future Activity | 0 | 2802 | NO | OUTPUT p/Testes Internos - TEN - CWE (T6/T7) | 0d |  | 2027-02-18 08:00 | 2027-02-17 16:00 |  | 0 | 2869FS;2870FS;3322FS;3323FS | 2803FS |  | NO
| Future Activity | 0 | 2803 | NO | Testes DEMO4 - Internas - TEN - CWE (T6/T7) | 5d |  | 2027-02-18 08:00 | 2027-02-24 16:00 | GENERICO - ATS Application | 45 | 2802FS | 3344FS;3345FS |  | NO
| Future Activity | 0 | 2804 | NO | OUTPUT p/Testes Internos - TES - CWE (T6/T7) | 0d |  | 2027-03-11 08:00 | 2027-03-10 16:00 |  | 0 | 2897FS;2898FS;3222FS;3223FS | 2805FS |  | NO
| Future Activity | 0 | 2805 | NO | Testes DEMO4 - Internas - TES - CWE (T6/T7) | 5d |  | 2027-03-11 08:00 | 2027-03-17 16:00 | GENERICO - ATS Application | 45 | 2804FS | 3246FS;3247FS |  | NO
| Future Activity | 0 | 2806 | NO | OUTPUT p/Testes Internos - TSG - CWE (T6/T7) | 0d |  | 2027-03-25 08:00 | 2027-03-24 16:00 |  | 0 | 2853FS;2854FS;3265FS | 2807FS |  | NO
| Future Activity | 0 | 2807 | NO | Testes DEMO4 - Internas - TSG - CWE (T6/T7) | 5d |  | 2027-03-25 08:00 | 2027-04-01 16:00 | GENERICO - ATS Application | 54 | 2806FS | 3301FS;3302FS |  | NO
| Future Activity | 0 | 2826 | NO | Baselines | 170d |  | 2026-10-06 08:00 | 2027-05-31 16:00 |  | 0 |  |  | -277d | YES
| Future Activity | 0 | 2827 | NO | Criação pacote de instalação - DEMO3 - Interna - BL? | 22d |  | 2026-10-06 08:00 | 2026-11-04 16:00 |  | 0 |  |  | -320d | YES
| Future Activity | 0 | 2828 | NO | Baseline KEPServer - DEMO3 - Interna | 10d |  | 2026-10-06 08:00 | 2026-10-20 16:00 |  | 0 | 3172FS | 2829FS;3171FS | -319d | NO
| Future Activity | 0 | 2829 | NO | Baseline SCADA - DEMO3 - Interna | 10d |  | 2026-10-21 08:00 | 2026-11-04 16:00 |  | 0 | 2828FS | 3FS | -320d | NO
| Future Activity | 0 | 2830 | NO | Criação pacote de instalação - DEMO3 - Cliente - BL? | 22d |  | 2027-04-30 08:00 | 2027-05-31 16:00 |  | 0 |  |  | -277d | YES
| Future Activity | 0 | 2831 | NO | Baseline KEPServer - DEMO3 - Cliente | 10d |  | 2027-04-30 08:00 | 2027-05-13 16:00 |  | 0 | 3174FS | 2832FS | -273d | NO
| Future Activity | 0 | 2832 | NO | Baseline SCADA - DEMO3 - Cliente | 10d |  | 2027-05-14 08:00 | 2027-05-31 16:00 |  | 0 | 2831FS | 3175FS | -277d | NO
| Confirmed | 0 | 1492 | NO | SCADA Sub System Engineering & Design SC200 | 156d |  | 2025-10-15 08:00 | 2026-06-16 16:00 |  | 305 |  |  | -20166d | YES
| Future Activity | 0 | 1494 | NO | Dataprep - TES (CWI) - Casetas - T6 & T7 | 10d | 2026-05-04 08:00 | 2026-05-04 08:00 | 2026-05-15 16:00 | Belini Thais,Pereira Davi | 134 | 2908FS | 1498FS;3359FS;3362FS | -77d | NO
| Future Activity | 0 | 1496 | NO | Dataprep - TSG (CWI) - Casetas - T6 & T7 | 10d | 2026-04-22 08:00 | 2026-04-22 08:00 | 2026-05-06 16:00 | Oda Robson | 99 | 1495FS;1500FS;2927FS;2999FS;3064FS | 1501FS;1501FS;3006FS | 92d | NO
| Future Activity | 0 | 1498 | NO | DI com End. de Campo - TES (CWI) - Casetas - T6 & T7 | 3d |  | 2026-05-18 08:00 | 2026-05-20 16:00 | Pereira Davi | 27 | 1494FS | 2904FS;3022FS | -170d | NO
| Future Activity | 0 | 1501 | NO | DI com End. de Campo - TSG (CWI) - Casetas - T6 & T7 | 5d |  | 2026-06-10 08:00 | 2026-06-16 16:00 | Pereira Davi | 45 | 1496FS;1496FS;3005FS | 2840FS;2853FS;2854FS | -145d | NO
| Confirmed | 97.4939 | 3113 | NO | SCADA Sub System Application Design / SW Development | 1452d |  | 2021-06-09 08:00 | 2027-06-14 16:00 |  | 6382.2397 |  |  | -228d | YES
| Confirmed | 97.4952 | 3126 | NO | SCADA MMI Activities | 1344d |  | 2021-06-09 08:00 | 2026-12-30 16:00 |  | 65.6712 |  |  | -355d | YES
| Confirmed | 86.5856 | 3161 | NO | SCADA MMI V1 Tramos 1-5 - FAT 5 | 1344d |  | 2021-06-09 08:00 | 2026-12-30 16:00 |  | 65.6712 |  |  | -355d | YES
| Confirmed | 86.5856 | 3162 | NO | Desenvolvimento IHM - CWE | 1344d |  | 2021-06-09 08:00 | 2026-12-30 16:00 |  | 65.6712 |  |  | -355d | YES
| Confirmed | 83.3741 | 3167 | NO | LE - MXTM - DH SW FuP | 1227d | 2021-12-01 08:00 | 2021-12-01 08:00 | 2026-12-30 16:00 | FIRMINO FERNANDO | 65.6712 | 2FS | 3FS | -355d | NO
| Confirmed | 60 | 3114 | NO | Atividades UHMI GAPs | 1402d |  | 2021-06-09 08:00 | 2027-03-31 16:00 |  | 226 |  |  | -274d | YES
| Future Activity | 0 | 3121 | NO | [OUTPUT] Versão SCADA - Territory M/ Geo T / Alarm - Demo 3 v1 | 0d |  | 2026-09-22 08:00 | 2026-09-21 16:00 |  | 0 | 3211FS | 960FS;1053FS;1054FS;1055FS;3172FS | -320d | NO
| Future Activity | 0 | 3122 | NO | [OUTPUT] Versão SCADA - Territory M/ Geo T / Alarm - Demo 3 v2 | 0d |  | 2027-04-01 08:00 | 2027-03-31 16:00 |  | 0 | 3124FS;3354FS | 3171FS | -274d | NO
| Future Activity | 0 | 3123 | NO | [OUTPUT] Versão UHMI 2.12 | 0d |  | 2026-11-24 08:00 | 2026-11-23 16:00 |  | 0 | 992FS;3119FS | 3FS | -311d | NO
| Confirmed | 0 | 3124 | NO | Correções de CRs - Versão SCADA - Territory M/ Geo T / Alarm | 446d |  | 2025-05-26 08:00 | 2027-03-31 16:00 |  | 226 |  | 3122FS | -274d | YES
| Confirmed | 0 | 3125 | NO | Ferramenta de Automação de desenvolvimento | 446d | 2025-05-26 08:00 | 2025-05-26 08:00 | 2027-03-31 16:00 | Santos Lucas | 226 | 2FS | 3FS | -274d | NO
| Confirmed | 15.0738 | 3168 | NO | SCADA UHMI | 1452d |  | 2021-06-09 08:00 | 2027-06-14 16:00 |  | 6090.5684 |  |  | -228d | YES
| Confirmed | 45.5411 | 3176 | NO | Generic Application | 1459d |  | 2021-06-09 08:00 | 2027-01-11 16:00 |  | 1601.3684 |  |  | -432d | YES
| Confirmed | 45.4545 | 3194 | NO | Project Gaps Implementation | 1368d |  | 2021-06-09 08:00 | 2026-09-04 16:00 |  | 618 |  |  | 208d | YES
| Confirmed | 0 | 3200 | NO | Desenvolvimento de Novas Funções c/ Apoio Bangalore | 201d | 2025-07-01 08:00 | 2025-07-01 08:00 | 2026-04-30 16:00 | Oliveira Luiz Guilherme,Santos Lucas | 131 | 2FS | 3202FS | -30d | NO
| Confirmed | 0 | 3196 | NO | Configuração Navigation Synoptic - TEN | 120d | 2025-10-01 08:00 | 2025-10-01 08:00 | 2026-04-06 16:00 | Oliveira Luiz Guilherme | 89 | 3204FS | 3205FS |  | NO
| Future Activity | 0 | 3201 | NO | Configuração Alarm on Generic Device | 83d | 2026-03-02 08:00 | 2026-03-02 08:00 | 2026-07-02 16:00 | Santos Lucas | 183 | 3024FS;3195FS | 3197FS;3203FS;3205FS;3207FS;3210FS;3355SS | -146d | NO
| Future Activity | 0 | 3205 | NO | Configuração Navigation Synoptic - TES/TSG | 40d | 2026-05-01 08:00 | 2026-07-03 08:00 | 2026-08-27 16:00 | Santos Lucas | 161 | 3196FS;3201FS | 3197FS |  | NO
| Future Activity | 0 | 3197 | NO | Configuração Navigation Synoptic - TEN - DEMO | 3d |  | 2026-08-28 08:00 | 2026-09-01 16:00 | Oliveira Luiz Guilherme | 27 | 3201FS;3202FS;3205FS;3317FS | 3199FS;3210FS | -187d | NO
| Future Activity | 0 | 3199 | NO | Configuração Navigation Synoptic - TES/TSG - DEMO | 3d |  | 2026-09-02 08:00 | 2026-09-04 16:00 | Santos Lucas | 27 | 3197FS;3230FS;3234FS;3281FS;3289FS | 3210FS | -239d | NO
| Future Activity | 0 | 3206 | NO | Alarms & Events | 22d |  | 2026-07-03 08:00 | 2026-08-03 16:00 |  | 155 | 3193FS |  | -145d | YES
| Future Activity | 0 | 3207 | NO | Severity Adjustment | 20d | 2025-09-25 08:00 | 2026-07-03 08:00 | 2026-08-03 16:00 | Oliveira Luiz Guilherme,Santos Lucas | 155 | 3201FS | 3210FS | -145d | NO
| Confirmed | 33.3333 | 3208 | NO | UHMI Versions | 341d |  | 2025-06-02 08:00 | 2026-09-21 16:00 |  | 170 |  |  | -320d | YES
| Future Activity | 0 | 3210 | NO | Instalação da versão SCADA - Territory M/ Geo T / Alarm | 5d | 2025-07-01 08:00 | 2026-09-08 08:00 | 2026-09-14 16:00 | Oliveira Luiz Guilherme,Santos Lucas | 85 | 3181FS;3185FS;3197FS;3199FS;3201FS;3202FS;3207FS | 3211FS | -180d | NO
| Future Activity | 0 | 3211 | NO | Migração da aplicação - Territory M/ Geo T / Alarm | 5d |  | 2026-09-15 08:00 | 2026-09-21 16:00 | Oliveira Luiz Guilherme,Santos Lucas | 85 | 3210FS | 961FS;3121FS | -180d | NO
| Confirmed | 20 | 3178 | NO | HMI Config | 426d |  | 2025-05-26 08:00 | 2027-01-11 16:00 |  | 658.3684 |  |  | -437d | YES
| Confirmed | 40 | 3179 | NO | HMI Database Config | 426d |  | 2025-05-26 08:00 | 2027-01-11 16:00 |  | 613.3684 |  |  | -207d | YES
| Future Activity | 0 | 3180 | NO | CST Module - Protótipo | 100d | 2026-05-05 08:00 | 2026-05-05 08:00 | 2026-09-21 16:00 | Oliveira Luiz Guilherme | 217.3684 | 2FS | 3182FS |  | NO
| Future Activity | 0 | 3182 | NO | CST Module - Configuração | 73d | 2025-07-01 08:00 | 2026-09-22 08:00 | 2027-01-11 16:00 | Oliveira Luiz Guilherme | 360 | 3180FS;3181FS | 3FS | -207d | NO
| Future Activity | 0 | 3183 | NO | Active Directory Integration | 10d | 2025-07-01 08:00 | 2026-03-18 08:00 | 2026-03-31 16:00 | Oliveira Luiz Guilherme | 36 | 3064FS | 3FS | -137d | NO
| Future Activity | 0 | 3189 | NO | General OPC UA Configuration | 5d | 2025-07-01 08:00 | 2026-05-04 08:00 | 2026-05-08 16:00 |  | 45 |  |  | -213d | YES
| Future Activity | 0 | 3190 | NO | Links de tela PLO + OCS T3 | 5d | 2026-05-04 08:00 | 2026-05-04 08:00 | 2026-05-08 16:00 | Oliveira Luiz Guilherme | 45 | 3324FS | 3FS | -213d | NO
| Confirmed | 29.828 | 3212 | NO | Specific Application | 1519d |  | 2021-06-09 08:00 | 2027-04-05 16:00 |  | 3635.5 |  |  | -158d | YES
| Confirmed | 24.0079 | 3213 | NO | Telemando de Estaciones - TES | 1508d |  | 2021-06-09 08:00 | 2027-03-19 16:00 |  | 672 |  |  | -162d | YES
| Confirmed | 42.8571 | 3214 | NO | SCADA Layout Design | 440d |  | 2025-07-02 08:00 | 2027-03-09 16:00 |  | 445 |  |  | -551d | YES
| Confirmed | 28.5714 | 3224 | NO | Desenvolvimento de Telas - TES CWI | 277d |  | 2025-07-02 08:00 | 2026-07-23 16:00 |  | 153 |  |  | -20203d | YES
| Confirmed | 16.6667 | 3225 | NO | TyC | 277d |  | 2025-07-02 08:00 | 2026-07-23 16:00 |  | 153 |  |  | -20203d | YES
| Future Activity | 0 | 3231 | NO | Desenvolvimento de tela - TES (CWI) - Cocheras de Campeche | 5d | 2026-06-02 08:00 | 2026-06-02 08:00 | 2026-06-10 16:00 | Oliveira Luiz Guilherme | 45 | 2949FS;2954FS;3359FS | 3229FS;3253FS | -124d | NO
| Future Activity | 0 | 3229 | NO | Desenvolvimento de tela - TES (CWI) - Cocheras de Mérida [João Oliveira 45H] | 5d |  | 2026-06-11 08:00 | 2026-06-17 16:00 |  | 0 | 2950FS;3231FS | 3228FS;3254FS | -124d | NO
| Future Activity | 0 | 3228 | NO | Desenvolvimento de tela - TES (CWI) - Cocheras de Tulúm | 5d |  | 2026-06-18 08:00 | 2026-06-24 16:00 | Oliveira Luiz Guilherme | 27 | 2951FS;3229FS | 3227FS;3251FS | -119d | NO
| Future Activity | 0 | 3227 | NO | Desenvolvimento de tela - TES (CWI) - TyC Escárcega | 5d |  | 2026-07-08 08:00 | 2026-07-16 16:00 | Oliveira Luiz Guilherme | 36 | 2952FS;3228FS;3285FS | 3226FS;3250FS | -98d | NO
| Future Activity | 0 | 3226 | NO | Desenvolvimento de tela - TES (CWI) - TyC Chetumal | 5d |  | 2026-07-17 08:00 | 2026-07-23 16:00 | Oliveira Luiz Guilherme | 45 | 2953FS;3227FS | 3252FS | -98d | NO
| Future Activity | 0 | 3215 | NO | Desenvolvimento de Telas - TES CWE | 157d |  | 2026-08-03 08:00 | 2027-03-09 16:00 |  | 292 |  |  | -20432d | YES
| Future Activity | 0 | 3216 | NO | Estações | 157d |  | 2026-08-03 08:00 | 2027-03-09 16:00 |  | 292 |  |  | -20432d | YES
| Future Activity | 0 | 3217 | NO | Desenvolvimento de tela - TES (CWE) - T3 - Estações | 5d |  | 2026-08-03 08:00 | 2026-08-07 16:00 | Oliveira Luiz Guilherme | 45 | 2936FS | 3FS;2783FS;3088FS | -196d | NO
| Future Activity | 0 | 3218 | NO | Desenvolvimento de tela - TES (CWE) - T4 - Estações | 5d |  | 2026-09-07 08:00 | 2026-09-11 16:00 | Oliveira Luiz Guilherme | 36 | 2937FS | 3FS;2783FS;3088FS | -177d | NO
| Future Activity | 0 | 3219 | NO | Desenvolvimento de tela - TES (CWE) - T1 - Estações | 5d |  | 2026-10-21 08:00 | 2026-10-27 16:00 | Oliveira Luiz Guilherme | 40 | 2938FS | 3FS;2790FS;3095FS | -176d | NO
| Future Activity | 0 | 3220 | NO | Desenvolvimento de tela - TES (CWE) - T2 - Estações | 5d |  | 2026-11-27 08:00 | 2026-12-03 16:00 | Oliveira Luiz Guilherme | 45 | 2939FS | 3FS;2790FS;3095FS | -177d | NO
| Future Activity | 0 | 3221 | NO | Desenvolvimento de tela - TES (CWE) - T5 - Estações | 5d |  | 2026-12-18 08:00 | 2026-12-24 16:00 | Oliveira Luiz Guilherme | 36 | 2940FS | 3FS;2797FS;3102FS | -175d | NO
| Future Activity | 0 | 3222 | NO | Desenvolvimento de tela - TES (CWE) - T6 - Estações | 5d |  | 2027-01-29 08:00 | 2027-02-04 16:00 | Oliveira Luiz Guilherme | 45 | 2941FS | 3FS;2804FS;3109FS | -178d | NO
| Future Activity | 0 | 3223 | NO | Desenvolvimento de tela - TES (CWE) - T7 - Estações | 5d |  | 2027-03-03 08:00 | 2027-03-09 16:00 | Oliveira Luiz Guilherme | 45 | 2942FS | 2804FS;3109FS | -183d | NO
| Confirmed | 29.1667 | 3237 | NO | Integration Open Points | 341d |  | 2025-11-28 08:00 | 2027-03-19 16:00 |  | 227 |  |  | -162d | YES
| Future Activity | 0 | 3239 | NO | Correções pós V&V CRs - TES CWI - IHM | 15d |  | 2026-03-18 08:00 | 2026-04-08 16:00 | Santos Lucas | 119 | 1040SS+5d | 956FS |  | NO
| Future Activity | 0 | 3240 | NO | Estações | 126d |  | 2026-09-25 08:00 | 2027-03-19 16:00 |  | 63 |  |  | -162d | YES
| Future Activity | 0 | 3241 | NO | Open Points Development - TES - T3- Estações | 1d |  | 2026-09-25 08:00 | 2026-09-25 16:00 | Santos Lucas | 9 | 2784FS | 3088FS;3242FS | -10d | NO
| Future Activity | 0 | 3242 | NO | Open Points Development - TES - T4- Estações | 1d |  | 2026-09-28 08:00 | 2026-09-28 16:00 | Santos Lucas | 9 | 2784FS;3241FS | 3088FS;3243FS | -12d | NO
| Future Activity | 0 | 3243 | NO | Open Points Development - TES - T1- Estações | 1d |  | 2026-12-16 08:00 | 2026-12-16 16:00 | Santos Lucas | 9 | 2791FS;3242FS | 3095FS;3244FS | -90d | NO
| Future Activity | 0 | 3244 | NO | Open Points Development - TES - T2- Estações | 1d |  | 2026-12-17 08:00 | 2026-12-17 16:00 | Santos Lucas | 9 | 2791FS;3243FS | 3095FS;3245FS | -90d | NO
| Future Activity | 0 | 3245 | NO | Open Points Development - TES - T5- Estações | 1d |  | 2027-01-07 08:00 | 2027-01-07 16:00 | Santos Lucas | 9 | 2798FS;3244FS | 3102FS;3246FS | -108d | NO
| Future Activity | 0 | 3246 | NO | Open Points Development - TES - T6- Estações | 1d |  | 2027-03-18 08:00 | 2027-03-18 16:00 | Santos Lucas | 9 | 2805FS;3245FS | 3109FS;3247FS | -177d | NO
| Future Activity | 0 | 3247 | NO | Open Points Development - TES - T7- Estações | 1d |  | 2027-03-19 08:00 | 2027-03-19 16:00 | Santos Lucas | 9 | 2805FS;3246FS | 3109FS | -177d | NO
| Confirmed | 16.6667 | 3248 | NO | TyC | 171d |  | 2025-11-28 08:00 | 2026-07-24 16:00 |  | 45 |  |  | -199d | YES
| Future Activity | 0 | 3253 | NO | Open Points Development - TES - Cochera Campeche | 1d |  | 2026-06-11 08:00 | 2026-06-11 16:00 | Oliveira Luiz Guilherme | 9 | 2906FS;3231FS;3364FS;3370FS | 3254FS |  | NO
| Future Activity | 0 | 3254 | NO | Open Points Development - TES - Cocheras de Mérida | 1d |  | 2026-06-18 08:00 | 2026-06-18 16:00 | Oliveira Luiz Guilherme | 9 | 3229FS;3253FS | 3251FS |  | NO
| Future Activity | 0 | 3251 | NO | Open Points Development - TES - Cocheras de Tulúm | 1d |  | 2026-06-25 08:00 | 2026-06-25 16:00 | Oliveira Luiz Guilherme | 9 | 3228FS;3254FS | 3250FS |  | NO
| Future Activity | 0 | 3250 | NO | Open Points Development - TES - TyC Escárcega | 1d | 2026-04-29 08:00 | 2026-07-17 08:00 | 2026-07-17 16:00 | Oliveira Luiz Guilherme | 9 | 3227FS;3249FS;3251FS | 3252FS |  | NO
| Future Activity | 0 | 3252 | NO | Open Points Development - TES - TyC Chetumal | 1d |  | 2026-07-24 08:00 | 2026-07-24 16:00 | Oliveira Luiz Guilherme | 9 | 3226FS;3250FS | 3FS |  | NO
| Confirmed | 44.7619 | 3255 | NO | Telemando de Seguridad - TSG | 460d |  | 2025-07-01 08:00 | 2027-04-05 16:00 |  | 1689.5 |  |  | -178d | YES
| Confirmed | 40.9524 | 3257 | NO | SCADA Layout Design | 439d | 2025-07-01 08:00 | 2025-07-01 08:00 | 2027-03-05 16:00 |  | 1365.5 |  |  | -415d | YES
| Future Activity | 0 | 3290 | NO | Layout Design Tela de emergencia | 5d | 2026-05-01 08:00 | 2026-05-04 08:00 | 2026-05-08 16:00 | Oliveira Luiz Guilherme | 45 | 2FS | 3FS | -154d | NO
| Future Activity | 0 | 3291 | NO | S2K OPC Tag Configuration | 20d | 2025-07-01 08:00 | 2026-11-05 08:00 | 2026-12-03 16:00 | Oliveira Luiz Guilherme,Santos Lucas | 345 | 2857FS | 3FS | -175d | NO
| Confirmed | 66.6667 | 3275 | NO | Desenvolvimento de Telas - TSG CWI | 266d |  | 2025-07-01 08:00 | 2026-07-07 16:00 |  | 180 |  |  | -20187d | YES
| Confirmed | 60 | 3276 | NO | TyC - TSG CWI | 266d |  | 2025-07-01 08:00 | 2026-07-07 16:00 |  | 180 |  |  | -20187d | YES
| Future Activity | 0 | 3283 | NO | Desenvolvimento de tela - TSG (CWI) - Cocheras de Mérida | 5d | 2026-06-01 08:00 | 2026-06-10 08:00 | 2026-06-16 16:00 | Santos Lucas | 45 | 3005FS;3280FS | 3286FS;3347FS |  | NO
| Future Activity | 0 | 3286 | NO | Desenvolvimento de tela - TSG (CWI) - Cocheras de Tulúm | 5d |  | 2026-06-17 08:00 | 2026-06-23 16:00 | Santos Lucas | 45 | 3006FS;3283FS | 3284FS |  | NO
| Future Activity | 0 | 3284 | NO | Desenvolvimento de tela - TSG (CWI) - TyC Escárcega | 5d |  | 2026-06-24 08:00 | 2026-06-30 16:00 | Santos Lucas | 45 | 3007FS;3286FS | 3285FS |  | NO
| Future Activity | 0 | 3285 | NO | Desenvolvimento de tela - TSG (CWI) - TyC Chetumal | 5d |  | 2026-07-01 08:00 | 2026-07-07 16:00 | Santos Lucas | 45 | 3003FS;3284FS | 3227FS;3304FS |  | NO
| Future Activity | 0 | 3266 | NO | Desenvolvimento de Telas - TSG CWE | 99d |  | 2026-10-20 08:00 | 2027-03-05 16:00 |  | 270 |  |  | -20428d | YES
| Future Activity | 0 | 3267 | NO | Estações - TSG CWE | 99d |  | 2026-10-20 08:00 | 2027-03-05 16:00 |  | 270 |  |  | -20428d | YES
| Future Activity | 0 | 3268 | NO | Desenvolvimento de tela - TSG (CWE) - T1- Estações | 5d |  | 2026-10-20 08:00 | 2026-10-26 16:00 | Santos Lucas | 45 | 3010FS | 3FS | -145d | NO
| Future Activity | 0 | 3274 | NO | Desenvolvimento de tela - TSG (CWE) - T2- Estações | 5d |  | 2026-11-11 08:00 | 2026-11-17 16:00 | Santos Lucas | 45 | 3011FS | 3FS | -144d | NO
| Future Activity | 0 | 3273 | NO | Desenvolvimento de tela - TSG (CWE) - T3- Estações | 5d |  | 2026-12-08 08:00 | 2026-12-14 16:00 | Santos Lucas | 45 | 3012FS | 3FS | -143d | NO
| Future Activity | 0 | 3272 | NO | Desenvolvimento de tela - TSG (CWE) - T4- Estações | 5d |  | 2026-12-31 08:00 | 2027-01-06 16:00 | Santos Lucas | 27 | 3013FS | 3FS | -145d | NO
| Future Activity | 0 | 3271 | NO | Desenvolvimento de tela - TSG (CWE) - T5- Estações | 5d |  | 2027-01-15 08:00 | 2027-01-21 16:00 | Santos Lucas | 45 | 3014FS | 3FS | -147d | NO
| Future Activity | 0 | 3270 | NO | Desenvolvimento de tela - TSG (CWE) - T6- Estações | 5d |  | 2027-02-08 08:00 | 2027-02-12 16:00 | Santos Lucas | 18 | 3015FS | 3FS | -147d | NO
| Future Activity | 0 | 3269 | NO | Desenvolvimento de tela - TSG (CWE) - T7- Estações | 5d |  | 2027-03-01 08:00 | 2027-03-05 16:00 | Santos Lucas | 45 | 3016FS |  | -150d | NO
| Confirmed | 20 | 3260 | NO | Desenvolvimento de Telas - TSG ISM | 300d |  | 2025-07-17 08:00 | 2026-09-09 16:00 |  | 525.5 |  |  | -20251d | YES
| Future Activity | 0 | 3262 | NO | Desenvolvimento de Telas - TSG (ISM) - T1 a T4 - Casetas e TyC | 27d |  | 2026-06-16 08:00 | 2026-07-22 16:00 | Belini Thais,OLIVEIRA JOAO,Santos Lucas | 60 | 3020FS;3022FS | 3FS;2785FS;2792FS;3263FS;3296FS | 23d | NO
| Future Activity | 0 | 3264 | NO | Desenvolvimento de Telas - TSG (ISM) - T1 a T4 - Estações | 22d | 2026-06-01 08:00 | 2026-06-01 08:00 | 2026-06-30 16:00 | Oliveira Luiz Guilherme | 193 | 3020FS | 3FS;2785FS;2792FS;3377FS |  | NO
| Confirmed | 0 | 3265 | NO | Desenvolvimento de Telas - TSG (ISM) - T5 a T7 - Casetas e TyC | 35d | 2026-02-02 08:00 | 2026-02-02 08:00 | 2026-03-20 16:00 | Oliveira Luiz Guilherme,Santos Lucas | 112.5 | 3021FS | 3FS;2806FS |  | NO
| Future Activity | 0 | 3263 | NO | Desenvolvimento de Telas - TSG (ISM) - T5 a T7 - Estações | 35d | 2026-02-02 08:00 | 2026-07-23 08:00 | 2026-09-09 16:00 | Santos Lucas | 160 | 3262FS | 3FS;2799FS;3304FS |  | NO
| Confirmed | 38.0952 | 3292 | NO | Integration Open Points | 321d |  | 2026-01-10 08:00 | 2027-04-05 16:00 |  | 288 |  |  | -178d | YES
| Future Activity | 0 | 3295 | NO | Estações | 80d |  | 2026-12-15 08:00 | 2027-04-05 16:00 |  | 63 |  |  | -178d | YES
| Future Activity | 0 | 3296 | NO | Open Points Development - TSG - T3- Estações | 1d | 2025-05-26 08:00 | 2026-12-15 08:00 | 2026-12-15 16:00 | Oliveira Luiz Guilherme | 9 | 2786FS;3262FS | 3090FS;3297FS | -75d | NO
| Future Activity | 0 | 3297 | NO | Open Points Development - TSG - T4- Estações | 1d |  | 2026-12-16 08:00 | 2026-12-16 16:00 | Oliveira Luiz Guilherme | 9 | 2786FS;2849FS+5d;3296FS | 3090FS;3298FS | -75d | NO
| Future Activity | 0 | 3298 | NO | Open Points Development - TSG - T1- Estações | 1d |  | 2027-02-05 08:00 | 2027-02-05 16:00 | Oliveira Luiz Guilherme | 9 | 2793FS;3297FS | 3097FS;3299FS | -123d | NO
| Future Activity | 0 | 3299 | NO | Open Points Development - TSG - T2- Estações | 1d |  | 2027-02-11 08:00 | 2027-02-11 16:00 | Oliveira Luiz Guilherme | 9 | 2793FS;3298FS | 3097FS;3300FS | -128d | NO
| Future Activity | 0 | 3300 | NO | Open Points Development - TSG - T5- Estações | 1d |  | 2027-02-23 08:00 | 2027-02-23 16:00 | Oliveira Luiz Guilherme | 9 | 2800FS;3299FS | 3104FS;3301FS | -139d | NO
| Future Activity | 0 | 3301 | NO | Open Points Development - TSG - T6- Estações | 1d |  | 2027-04-02 08:00 | 2027-04-02 16:00 | Oliveira Luiz Guilherme | 9 | 2807FS;3300FS | 3111FS;3302FS | -176d | NO
| Future Activity | 0 | 3302 | NO | Open Points Development - TSG - T7- Estações | 1d |  | 2027-04-05 08:00 | 2027-04-05 16:00 | Oliveira Luiz Guilherme | 9 | 2807FS;3301FS | 3111FS | -178d | NO
| Confirmed | 14.2857 | 3303 | NO | TyC | 194d |  | 2026-01-12 08:00 | 2026-10-08 16:00 |  | 225 |  |  | -209d | YES
| Future Activity | 0 | 3304 | NO | Open Points Development - TSG - Cochera Campeche | 1d | 2026-03-09 08:00 | 2026-09-10 08:00 | 2026-09-10 16:00 | Santos Lucas | 9 | 2842FS;3263FS;3285FS | 3305FS;3308FS | -212d | NO
| Future Activity | 0 | 3305 | NO | Open Points Development - TSG - Cocheras de Mérida | 1d |  | 2026-09-11 08:00 | 2026-09-11 16:00 | Santos Lucas | 9 | 3304FS | 3306FS | -212d | NO
| Future Activity | 0 | 3306 | NO | Open Points Development - TSG - Cocheras de Tulúm | 1d |  | 2026-09-14 08:00 | 2026-09-14 16:00 | Santos Lucas | 9 | 3305FS | 3FS;3309FS | -214d | NO
| Future Activity | 0 | 3309 | NO | Open Points Development - TSG - TyC Escárcega | 1d |  | 2026-09-15 08:00 | 2026-09-15 16:00 | Santos Lucas | 9 | 3306FS;3307FS | 3310FS |  | NO
| Future Activity | 0 | 3310 | NO | Open Points Development - TSG - TyC Chetumal | 1d |  | 2026-09-16 08:00 | 2026-09-16 16:00 | Santos Lucas | 9 | 3309FS | 3FS;3383FS |  | NO
| Future Activity | 0 | 3308 | NO | DAU | 20d | 2026-03-09 08:00 | 2026-09-11 08:00 | 2026-10-08 16:00 | Oliveira Luiz Guilherme | 180 | 3304FS | 3FS | -209d | NO
| Future Activity | 0 | 3256 | NO | Correções pós V&V CRs - TSG CWI - IHM | 10d |  | 2026-03-18 08:00 | 2026-03-31 16:00 | Oliveira Luiz Guilherme | 36 | 1050SS+5d | 956FS |  | NO
| Confirmed | 20.7143 | 3312 | NO | Telemando de Energia - TEN | 449d |  | 2025-06-09 08:00 | 2027-02-25 16:00 |  | 1274 |  |  | -119d | YES
| Future Activity | 0 | 3313 | NO | Correções pós V&V CRs - TEN CFE CWI - IHM DEMO | 7d |  | 2026-03-06 08:00 | 2026-03-16 16:00 | Oliveira Luiz Guilherme | 18 | 1041FS-3d | 3075FS |  | NO
| Confirmed | 40 | 3329 | NO | S2K OPC Tag Configuration | 335d |  | 2025-06-09 08:00 | 2026-09-18 16:00 |  | 260 |  |  | -73d | YES
| Future Activity | 0 | 3332 | NO | PLO OPC Tags link - T4 | 5d | 2025-07-01 08:00 | 2026-07-17 08:00 | 2026-07-23 16:00 | Oliveira Luiz Guilherme,Santos Lucas | 90 | 2986FS | 3325FS | -134d | NO
| Future Activity | 0 | 3334 | NO | PLO OPC Tags link - T5 | 5d | 2025-07-01 08:00 | 2026-08-14 08:00 | 2026-08-20 16:00 | Oliveira Luiz Guilherme,Santos Lucas | 90 | 2987FS | 3326FS | -72d | NO
| Future Activity | 0 | 3333 | NO | PLO OPC Tags link - T6 | 5d | 2025-07-01 08:00 | 2026-09-14 08:00 | 2026-09-18 16:00 | Oliveira Luiz Guilherme,Santos Lucas | 80 | 2988FS | 3327FS | -73d | NO
| Confirmed | 42.8571 | 3314 | NO | SCADA Layout Design | 413d |  | 2025-06-16 08:00 | 2027-01-13 16:00 |  | 690 |  |  | -344d | YES
| Future Activity | 0 | 3325 | NO | PLO Screens Design - T4 | 5d |  | 2026-07-24 08:00 | 2026-07-30 16:00 | Oliveira Luiz Guilherme | 45 | 3332FS | 3FS | -134d | NO
| Future Activity | 0 | 3326 | NO | PLO Screens Design - T5 | 5d |  | 2026-08-21 08:00 | 2026-08-27 16:00 | Oliveira Luiz Guilherme | 45 | 3334FS | 3FS | -72d | NO
| Future Activity | 0 | 3327 | NO | PLO Screens Design - T6 | 5d |  | 2026-09-21 08:00 | 2026-09-25 16:00 | Oliveira Luiz Guilherme | 40 | 3333FS | 3FS | -71d | NO
| Future Activity | 0 | 3316 | NO | Desenvolvimento de Telas - TEN CWE | 115d |  | 2026-08-06 08:00 | 2027-01-13 16:00 |  | 560 |  |  | -147d | YES
| Future Activity | 0 | 3317 | NO | Desenvolvimento de tela - TEN (CWE) - T3 - Estações | 10d |  | 2026-08-06 08:00 | 2026-08-19 16:00 | Oliveira Luiz Guilherme | 90 | 2971FS | 2781FS;3197FS;3318FS;3339FS | -177d | NO
| Future Activity | 0 | 3318 | NO | Desenvolvimento de tela - TEN (CWE) - T4 - Estações | 10d |  | 2026-08-27 08:00 | 2026-09-10 16:00 | Oliveira Luiz Guilherme | 70 | 2972FS;3317FS | 2781FS;3319FS;3340FS | -147d | NO
| Future Activity | 0 | 3319 | NO | Desenvolvimento de tela - TEN (CWE) - T1 - Estações | 10d |  | 2026-09-23 08:00 | 2026-10-06 16:00 | Oliveira Luiz Guilherme | 90 | 2973FS;3318FS | 2788FS;3320FS;3341FS | -144d | NO
| Future Activity | 0 | 3320 | NO | Desenvolvimento de tela - TEN (CWE) - T2 - Estações | 10d |  | 2026-11-04 08:00 | 2026-11-17 16:00 | Oliveira Luiz Guilherme | 70 | 2974FS;3319FS | 2788FS;3321FS;3342FS | -144d | NO
| Future Activity | 0 | 3321 | NO | Desenvolvimento de tela - TEN (CWE) - T5 - Estações | 10d |  | 2026-11-18 08:00 | 2026-12-02 16:00 | Oliveira Luiz Guilherme | 80 | 2975FS;3320FS | 2795FS;3322FS;3343FS | -141d | NO
| Future Activity | 0 | 3322 | NO | Desenvolvimento de tela - TEN (CWE) - T6 - Estações | 10d |  | 2026-12-09 08:00 | 2026-12-22 16:00 | Oliveira Luiz Guilherme | 80 | 2976FS;3321FS | 2802FS;3323FS;3344FS | -141d | NO
| Future Activity | 0 | 3323 | NO | Desenvolvimento de tela - TEN (CWE) - T7 - Estações | 10d |  | 2026-12-29 08:00 | 2027-01-13 16:00 | Oliveira Luiz Guilherme | 80 | 2977FS;3322FS | 2802FS;3345FS | -147d | NO
| Future Activity | 0 | 3335 | NO | Integration Open Points | 259d |  | 2026-03-02 08:00 | 2027-02-25 16:00 |  | 306 |  |  | -119d | YES
| Future Activity | 0 | 3336 | NO | Open Points - OCS | 4d |  | 2026-03-02 08:00 | 2026-03-05 16:00 | Oliveira Luiz Guilherme | 36 | 2809FS;2815FS | 3082FS |  | NO
| Future Activity | 0 | 3338 | NO | Estações | 79d |  | 2026-11-09 08:00 | 2027-02-25 16:00 |  | 63 |  |  | -139d | YES
| Future Activity | 0 | 3339 | NO | Open Points Development - TEN - T3- Estações | 1d |  | 2026-11-09 08:00 | 2026-11-09 16:00 | Oliveira Luiz Guilherme | 9 | 2782FS;2864FS;3317FS | 3086FS | -39d | NO
| Future Activity | 0 | 3340 | NO | Open Points Development - TEN - T4- Estações | 1d |  | 2026-11-09 08:00 | 2026-11-09 16:00 | Oliveira Luiz Guilherme | 9 | 2782FS;2865FS;3318FS | 3086FS | -38d | NO
| Future Activity | 0 | 3341 | NO | Open Points Development - TEN - T1- Estações | 1d |  | 2026-12-29 08:00 | 2026-12-29 16:00 | Oliveira Luiz Guilherme | 9 | 2789FS;2866FS;3319FS | 3093FS | -85d | NO
| Future Activity | 0 | 3342 | NO | Open Points Development - TEN - T2- Estações | 1d |  | 2026-12-29 08:00 | 2026-12-29 16:00 | Oliveira Luiz Guilherme | 9 | 2789FS;2867FS;3320FS | 3093FS;3343FS | -84d | NO
| Future Activity | 0 | 3343 | NO | Open Points Development - TEN - T5- Estações | 1d |  | 2027-01-13 08:00 | 2027-01-13 16:00 | Oliveira Luiz Guilherme | 9 | 2796FS;2868FS;3321FS;3342FS | 3100FS;3344FS | -98d | NO
| Future Activity | 0 | 3344 | NO | Open Points Development - TEN - T6- Estações | 1d |  | 2027-02-25 08:00 | 2027-02-25 16:00 | Oliveira Luiz Guilherme | 9 | 2803FS;2869FS;3322FS;3343FS | 3107FS | -140d | NO
| Future Activity | 0 | 3345 | NO | Open Points Development - TEN - T7- Estações | 1d |  | 2027-02-25 08:00 | 2027-02-25 16:00 | Oliveira Luiz Guilherme | 9 | 2803FS;2870FS;3323FS | 3107FS | -139d | NO
| Future Activity | 0 | 3346 | NO | TyC | 154d |  | 2026-03-02 08:00 | 2026-10-01 16:00 |  | 72 |  |  | 28d | YES
| Future Activity | 0 | 3347 | NO | Open Points Development - TEN - Cochera Campeche | 1d |  | 2026-09-25 08:00 | 2026-09-25 16:00 | Santos Lucas | 9 | 3283FS;3388FS | 3348FS | 27d | NO
| Future Activity | 0 | 3348 | NO | Open Points Development - TEN - Cocheras de Mérida | 1d |  | 2026-09-28 08:00 | 2026-09-28 16:00 | Santos Lucas | 9 | 3347FS | 3349FS | 25d | NO
| Future Activity | 0 | 3349 | NO | Open Points Development - TEN - Cocheras de Tulúm | 1d |  | 2026-09-29 08:00 | 2026-09-29 16:00 | Santos Lucas | 9 | 3348FS | 3351FS | 27d | NO
| Future Activity | 0 | 3350 | NO | Open Points Development - TEN - TyC Cancún - DEMO | 1d |  | 2026-03-02 08:00 | 2026-03-02 16:00 | Santos Lucas | 27 | 2815FS;3382FS | 3073FS;3351FS | 239d | NO
| Future Activity | 0 | 3351 | NO | Open Points Development - TEN - TyC Escárcega | 1d |  | 2026-09-30 08:00 | 2026-09-30 16:00 | Santos Lucas | 9 | 3349FS;3350FS | 3352FS | 28d | NO
| Future Activity | 0 | 3352 | NO | Open Points Development - TEN - TyC Chetumal | 1d |  | 2026-10-01 08:00 | 2026-10-01 16:00 | Santos Lucas | 9 | 3351FS |  | 28d | NO
| Future Activity | 0 | 3337 | NO | Correções pós V&V CRs - TEN CWI - IHM | 15d | 2026-04-27 08:00 | 2026-04-27 08:00 | 2026-05-18 16:00 | Santos Lucas | 135 | 1041SS+13d | 1034FS;3355FS;3383FS |  | NO
| Future Activity | 0 | 3353 | NO | UHMI Open Points | 124d |  | 2026-05-19 08:00 | 2026-11-06 16:00 |  | 493.7 |  |  | -318d | YES
| Future Activity | 0 | 3354 | NO | Correções de CRs - Versão SCADA - Territory M/ Geo T / Alarm - Demo 3 v2 | 20d | 2025-08-01 08:00 | 2026-10-08 08:00 | 2026-11-06 16:00 | Oliveira Luiz Guilherme,Santos Lucas | 325 | 989FS | 962FS;3122FS | -318d | NO
| Future Activity | 0 | 3355 | NO | Limitação de caracteres | 80d | 2026-04-01 08:00 | 2026-05-19 08:00 | 2026-09-14 16:00 | Santos Lucas | 168.7 | 3201SS;3337FS | 3FS | -360d | NO
| Future Activity | 0 | 3169 | NO | Baselines | 190d |  | 2026-09-22 08:00 | 2027-06-14 16:00 |  | 360 |  |  | -276d | YES
| Future Activity | 0 | 3170 | NO | Criação pacote de instalação - DEMO3 - Interna - BL? | 147d |  | 2026-09-22 08:00 | 2027-04-14 16:00 |  | 180 |  |  | -272d | YES
| Future Activity | 0 | 3172 | NO | Baseline IHM - DEMO3 - Interna | 10d | 2025-07-01 08:00 | 2026-09-22 08:00 | 2026-10-05 16:00 | Santos Lucas | 90 | 3121FS | 2828FS;3171FS | -320d | NO
| Future Activity | 0 | 3171 | NO | Baseline SCADA - DEMO3 - Interna IHM pós CRs | 10d |  | 2027-04-01 08:00 | 2027-04-14 16:00 | Santos Lucas | 90 | 2828FS;3122FS;3172FS | 3174FS | -272d | NO
| Future Activity | 0 | 3173 | NO | Criação pacote de instalação - DEMO3 - Cliente - BL? | 43d |  | 2027-04-15 08:00 | 2027-06-14 16:00 |  | 180 |  |  | -276d | YES
| Future Activity | 0 | 3174 | NO | Baseline IHM - DEMO3 - Cliente | 10d |  | 2027-04-15 08:00 | 2027-04-29 16:00 | Santos Lucas | 90 | 3171FS | 2831FS;3175FS | -273d | NO
| Future Activity | 0 | 3175 | NO | Baseline SCADA - DEMO3 - Cliente IHM | 10d |  | 2027-06-01 08:00 | 2027-06-14 16:00 | Santos Lucas | 90 | 2832FS;3174FS | 3FS | -276d | NO
| Confirmed | 0 | 3356 | NO | SCADA UHMI SC200 | 205d |  | 2025-11-12 08:00 | 2026-09-24 16:00 |  | 252 |  |  | -20266d | YES
| Confirmed | 50 | 3357 | NO | DI - SCADA UHMI SC200 - TES | 126d |  | 2025-11-12 08:00 | 2026-05-29 16:00 |  | 90 |  |  | -20148d | YES
| Future Activity | 0 | 3359 | NO | Desenvolvimento de tela - TES (CWI) - Casetas - T6 & T7 | 10d | 2026-04-22 08:00 | 2026-05-18 08:00 | 2026-05-29 16:00 | Oliveira Luiz Guilherme | 90 | 1494FS;3358FS | 3231FS;3362FS | -44d | NO
| Confirmed | 50 | 3360 | NO | DI - SCADA UHMI SC200 - TSG | 125d |  | 2025-12-01 08:00 | 2026-06-16 16:00 |  | 72 |  |  | -20166d | YES
| Future Activity | 0 | 3362 | NO | Desenvolvimento de tela - TSG (CWI) - T6 & T7 - Casetas | 10d |  | 2026-06-01 08:00 | 2026-06-16 16:00 | Oliveira Luiz Guilherme | 72 | 1494FS;3359FS;3361FS | 3281FS | 87d | NO
| Confirmed | 66.6667 | 3363 | NO | Open Points UHMI - SCADA UHMI SC200 - TES | 68d |  | 2026-01-12 08:00 | 2026-04-23 16:00 |  | 18 |  |  | -20112d | YES
| Future Activity | 0 | 3369 | NO | Open Points Development - TES - T6- Casetas | 1d | 2026-04-22 08:00 | 2026-04-22 08:00 | 2026-04-22 16:00 | Oliveira Luiz Guilherme | 9 | 3368FS | 3370FS | -13d | NO
| Future Activity | 0 | 3370 | NO | Open Points Development - TES - T7- Casetas | 1d |  | 2026-04-23 08:00 | 2026-04-23 16:00 | Oliveira Luiz Guilherme | 9 | 3369FS | 3253FS;3372FS | -13d | NO
| Future Activity | 0 | 3372 | NO | Output Open Points TES CWI Casetas - FAT - T6 & T7 | 0d |  | 2026-04-24 08:00 | 2026-04-23 16:00 |  | 0 | 3370FS |  |  | NO
| Confirmed | 71.4286 | 3373 | NO | Open Points UHMI - SCADA UHMI SC200 - TSG | 120d |  | 2026-01-05 08:00 | 2026-07-02 16:00 |  | 18 |  |  | -20182d | YES
| Future Activity | 0 | 3377 | NO | Open Points Development - TSG - T6- Casetas | 1d |  | 2026-07-01 08:00 | 2026-07-01 16:00 | Santos Lucas | 9 | 3264FS;3376FS | 3378FS | -145d | NO
| Future Activity | 0 | 3378 | NO | Open Points Development - TSG - T7- Casetas | 1d |  | 2026-07-02 08:00 | 2026-07-02 16:00 | Santos Lucas | 9 | 3377FS |  | -143d | NO
| Confirmed | 14.2857 | 3381 | NO | Open Points UHMI - SCADA UHMI SC200 - TEN | 143d |  | 2026-02-25 08:00 | 2026-09-24 16:00 |  | 54 |  |  | -20266d | YES
| Future Activity | 0 | 3383 | NO | Open Points Development - TEN - T2- Casetas | 1d | 2026-04-28 08:00 | 2026-09-17 08:00 | 2026-09-17 16:00 | Santos Lucas | 9 | 3310FS;3337FS;3382FS | 3384FS | 27d | NO
| Future Activity | 0 | 3384 | NO | Open Points Development - TEN - T3- Casetas | 1d |  | 2026-09-18 08:00 | 2026-09-18 16:00 | Santos Lucas | 9 | 3383FS | 3385FS | 27d | NO
| Future Activity | 0 | 3385 | NO | Open Points Development - TEN - T4- Casetas | 1d |  | 2026-09-21 08:00 | 2026-09-21 16:00 | Santos Lucas | 9 | 3384FS | 3386FS | 25d | NO
| Future Activity | 0 | 3386 | NO | Open Points Development - TEN - T5- Casetas | 1d |  | 2026-09-22 08:00 | 2026-09-22 16:00 | Santos Lucas | 9 | 3385FS | 3387FS | 27d | NO
| Future Activity | 0 | 3387 | NO | Open Points Development - TEN - T6- Casetas | 1d |  | 2026-09-23 08:00 | 2026-09-23 16:00 | Santos Lucas | 9 | 3386FS | 3388FS | 27d | NO
| Future Activity | 0 | 3388 | NO | Open Points Development - TEN - T7- Casetas | 1d |  | 2026-09-24 08:00 | 2026-09-24 16:00 | Santos Lucas | 9 | 3387FS | 3347FS | 27d | NO

## plw-metadata (hidden)
opx_version | 10
ts | 690568968b5c7dd7a118ea357ce29129559a9ef5accf3006